## 001
TCD DAILY FIELD REPORT
| Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-05
| Project Location: | Geraldton | [5 empty] | Day: | 2025-05-05
| Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
| Report Number: | 1 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 29 degrees Wind: 24 km/h E Precip: 0mm
PERSONNEL
| TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
| Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
| WATKINS, Steve | Civil Manager | 0 |  |  |  | Khegan Brockman | Labourer | 10
| GRIFFITHS, Daniel | Project Manager | 11
| GRIFFITHS, Ashley | Supervisor | 11
| Total Indirect Personnel onsite: | 2 |  |  |  |  | Total Subcontractor on-site: | 1
| Total Indirect Personnel hours: | 22 |  |  |  |  | Total Subcontractor hours: | 10
| Total Direct Personnel onsite: | 0
| Total Direct Personnel hours: | 0
PLANT & EQUIPMENT
| Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
| Komatsu WA320 | FWL18 | 5 |  |  | 1 | Office 40ft | 9255540 | 1
| Wacker Neuson DPU | DPC15 |  |  |  | 1 | Sea Container 20ft | 951200 | 1
| 0 | Repairs Required |  | N/A
| 0 | Scheduled Service |  | N/A
| 0 | Repairs required but operable |  | N/A
| Total Plant and Equipment Hours: |  | 2
DELAYS-OPPORTUNITY
HSEQ MESSAGES
| TCD - Monthly Safety Focus: | JHA
| TCD - Daily Safety Focus: | Loading and Unloading
| Hazards Reported: | Nil
| Incident Free Days | 5
Other Notes
INCIDENTS & REPORTS
|  | QTY | Comments
| INCIDENT | 0 | NA
| IR | 0 | NA
| NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Enabling compound-Running water and toilet
Commence install of site fencing
PHOTOS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## 002
TCD DAILY FIELD REPORT
| Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-06
| Project Location: | Geraldton | [5 empty] | Day: | 2025-05-06
| Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
| Report Number: | 2 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 26 degrees Wind: 22 km/h E Precip: 0mm
PERSONNEL
| TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
| Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
| WATKINS, Steve | Civil Manager | 0 |  |  |  | Khegan Brockman | Labourer | 10
| GRIFFITHS, Daniel | Project Manager | 11
| GRIFFITHS, Ashley | Supervisor | 11
| Total Indirect Personnel onsite: | 2 |  |  |  |  | Total Subcontractor on-site: | 1
| Total Indirect Personnel hours: | 22 |  |  |  |  | Total Subcontractor hours: | 10
| Total Direct Personnel onsite: | 0
| Total Direct Personnel hours: | 0
PLANT & EQUIPMENT
| Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
| Komatsu WA320 | FWL18 | 5 |  |  | 1 | Office 40ft | 9255540 | 1
| Wacker Neuson DPU | DPC15 |  |  |  | 1 | Sea Container 20ft | 951200 | 1
| 0 | Repairs Required |  | N/A
| 0 | Scheduled Service |  | N/A
| 0 | Repairs required but operable |  | N/A
| Total Plant and Equipment Hours: |  | 2
DELAYS-OPPORTUNITY
HSEQ MESSAGES
| TCD - Monthly Safety Focus: | JHA
| TCD - Daily Safety Focus: | PPE
| Hazards Reported: | Nil
| Incident Free Days | 6
Other Notes
INCIDENTS & REPORTS
|  | QTY | Comments
| INCIDENT | 0 | NA
| IR | 0 | NA
| NCR | 0 | NA
COMMUNICATIONS
APRA Issued to Watercorp
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Fencing Install
PHOTOS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## 003
TCD DAILY FIELD REPORT
| Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-07
| Project Location: | Geraldton | [5 empty] | Day: | 2025-05-07
| Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
| Report Number: | 3 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 30 degrees Wind: 23 km/h E Precip: 0mm
PERSONNEL
| TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
| Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
| WATKINS, Steve | Civil Manager | 0 |  |  |  | Khegan Brockman | Labourer | 10
| GRIFFITHS, Daniel | Project Manager | 11
| GRIFFITHS, Ashley | Supervisor | 11
| Total Indirect Personnel onsite: | 2 |  |  |  |  | Total Subcontractor on-site: | 1
| Total Indirect Personnel hours: | 22 |  |  |  |  | Total Subcontractor hours: | 10
| Total Direct Personnel onsite: | 0
| Total Direct Personnel hours: | 0
PLANT & EQUIPMENT
| Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
| Komatsu WA320 | FWL18 |  |  |  | 1 | Office 40ft | 9255540 | 1
| Wacker Neuson DPU | DPC15 |  |  |  | 1 | Sea Container 20ft | 951200 | 1
[6 empty] | 1 | Site Sentry Tower |  | 2
| 0 | Repairs Required |  | N/A
| 0 | Scheduled Service |  | N/A
| 0 | Repairs required but operable |  | N/A
| Total Plant and Equipment Hours: |  | 3
DELAYS-OPPORTUNITY
HSEQ MESSAGES
| TCD - Monthly Safety Focus: | JHA
| TCD - Daily Safety Focus: | Public Interaction
| Hazards Reported: | Nil
| Incident Free Days | 7
Other Notes
INCIDENTS & REPORTS
|  | QTY | Comments
| INCIDENT | 0 | NA
| IR | 0 | NA
| NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Complete Fencing Install
Establish Site Security Cameras
Demo of fencing in front of sump
Inspection of carpark works
PHOTOS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## 004
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-08
Project Location: | Geraldton | [5 empty] | Day: | 2025-05-08
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 4 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 35 degrees Wind: 35 km/h WE Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager | 0 |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10
GRIFFITHS, Ashley | Supervisor | 10
Total Indirect Personnel onsite: | 2 |  |  |  |  | Total Subcontractor on-site: | 1
Total Indirect Personnel hours: | 20 |  |  |  |  | Total Subcontractor hours: | 10
Total Direct Personnel onsite: | 0
Total Direct Personnel hours: | 0
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  |  |  |  | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  |  |  |  | Sea Container 20ft | 951200 | 1
[6 empty] | Site Sentry Tower |  | 2
[6 empty] | Skip Bin |  | 1
[6 empty] | Hydrocarbon Bund |  | 1
[6 empty] | Temp Fence |  | 1
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours: |  | 0
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Positive Comms
Hazards Reported: | Nil
Incident Free Days | 8
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Commence Demolition of Brick Pavers Within Site Boundary Bayly Street End
Received Survey
Delap Survey Inspected 8 Properties
Application in for Sewer Plugs
Demolish Fence Site Side of Sump
PHOTOS