## Table 1
TCD DAILY FIELD REPORT
Project Name: Batavia Station Square Date: 14/05/2025 Project Location: Geraldton Day: Wednesday Project Number: TCD-1816 Start: 7:00 Report Number: 8 Finish: 17:00
WEATHER & GROUND CONDITIONS
Temperature: 27 degrees Wind: 24 km/h E Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager | 10 |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10
GRIFFITHS, Ashley | Supervisor | 10
Total Indirect Personnel onsite: | 3 |  |  |  |  | Total Subcontractor on-site: | 1
Total Indirect Personnel hours: | 30 |  |  |  |  | Total Subcontractor hours: | 10
Total Direct Personnel onsite: | 0
Total Direct Personnel hours: | 0
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 |  |  |  | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  |  |  |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 03 | 2 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 6 |  |  |  | Skip Bin |  | 1
[6 empty] | Hydrocarbon Bund |  | 1
[6 empty] | Temp Fence |  | 1
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours: |  | 10
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Vehicles
Hazards Reported: | Nil
Incident Free Days | 12
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Complete Basin Topsoil Strip
Commence General Site Vegetation Strip
Fortnightly Progress Meeting
Meet with Maritime Museum and confirmed vibration monitor location
Drainage Order Placed
PHOTOS