## 001
TCD DAILY FIELD REPORT
| Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-05
| Project Location: | Geraldton | [5 empty] | Day:
| Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
| Report Number: | 1 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 29 degrees Wind: 24 km/h E Precip: 0mm
PERSONNEL
| TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
| Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
| WATKINS, Steve | Civil Manager | 0 |  |  |  | Khegan Brockman | Labourer | 10
| GRIFFITHS, Daniel | Project Manager | 11
| GRIFFITHS, Ashley | Supervisor | 11
| Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
| Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
| Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
| Komatsu WA320 | FWL18 | 5 |  |  | 1 | Office 40ft | 9255540 | 1
| Wacker Neuson DPU | DPC15 |  |  |  | 1 | Sea Container 20ft | 951200 | 1
| 0 | Repairs Required |  | N/A
| 0 | Scheduled Service |  | N/A
| 0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
| TCD - Monthly Safety Focus: | JHA
| TCD - Daily Safety Focus: | Loading and Unloading
| Hazards Reported: | Nil
| Incident Free Days | 5
Other Notes
INCIDENTS & REPORTS
|  | QTY | Comments
| INCIDENT | 0 | NA
| IR | 0 | NA
| NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Enabling compound-Running water and toilet
Commence install of site fencing
PHOTOS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## 002
TCD DAILY FIELD REPORT
| Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-06
| Project Location: | Geraldton | [5 empty] | Day:
| Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
| Report Number: | 2 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 26 degrees Wind: 22 km/h E Precip: 0mm
PERSONNEL
| TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
| Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
| WATKINS, Steve | Civil Manager | 0 |  |  |  | Khegan Brockman | Labourer | 10
| GRIFFITHS, Daniel | Project Manager | 11
| GRIFFITHS, Ashley | Supervisor | 11
| Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
| Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
| Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
| Komatsu WA320 | FWL18 | 5 |  |  | 1 | Office 40ft | 9255540 | 1
| Wacker Neuson DPU | DPC15 |  |  |  | 1 | Sea Container 20ft | 951200 | 1
| 0 | Repairs Required |  | N/A
| 0 | Scheduled Service |  | N/A
| 0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
| TCD - Monthly Safety Focus: | JHA
| TCD - Daily Safety Focus: | PPE
| Hazards Reported: | Nil
| Incident Free Days | 6
Other Notes
INCIDENTS & REPORTS
|  | QTY | Comments
| INCIDENT | 0 | NA
| IR | 0 | NA
| NCR | 0 | NA
COMMUNICATIONS
APRA Issued to Watercorp
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Fencing Install
PHOTOS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## 003
TCD DAILY FIELD REPORT
| Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-07
| Project Location: | Geraldton | [5 empty] | Day:
| Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
| Report Number: | 3 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 30 degrees Wind: 23 km/h E Precip: 0mm
PERSONNEL
| TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
| Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
| WATKINS, Steve | Civil Manager | 0 |  |  |  | Khegan Brockman | Labourer | 10
| GRIFFITHS, Daniel | Project Manager | 11
| GRIFFITHS, Ashley | Supervisor | 11
| Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
| Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
| Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
| Komatsu WA320 | FWL18 |  |  |  | 1 | Office 40ft | 9255540 | 1
| Wacker Neuson DPU | DPC15 |  |  |  | 1 | Sea Container 20ft | 951200 | 1
[6 empty] | 1 | Site Sentry Tower |  | 2
| 0 | Repairs Required |  | N/A
| 0 | Scheduled Service |  | N/A
| 0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
| TCD - Monthly Safety Focus: | JHA
| TCD - Daily Safety Focus: | Public Interaction
| Hazards Reported: | Nil
| Incident Free Days | 7
Other Notes
INCIDENTS & REPORTS
|  | QTY | Comments
| INCIDENT | 0 | NA
| IR | 0 | NA
| NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Complete Fencing Install
Establish Site Security Cameras
Demo of fencing in front of sump
Inspection of carpark works
PHOTOS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## 004
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-08
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 4 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 35 degrees Wind: 35 km/h WE Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager | 0 |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10
GRIFFITHS, Ashley | Supervisor | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  |  |  |  | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  |  |  |  | Sea Container 20ft | 951200 | 1
[6 empty] | Site Sentry Tower |  | 2
[6 empty] | Skip Bin |  | 1
[6 empty] | Hydrocarbon Bund |  | 1
[6 empty] | Temp Fence |  | 1
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Positive Comms
Hazards Reported: | Nil
Incident Free Days | 8
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Commence Demolition of Brick Pavers Within Site Boundary Bayly Street End
Received Survey
Delap Survey Inspected 8 Properties
Application in for Sewer Plugs
Demolish Fence Site Side of Sump
PHOTOS

## 005
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-09
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 5 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 34 degrees Wind: 325 km/h WE Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager | 0 |  |  |  | Khegan Brockman | Labourer | 5
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Jayden Brecz | Service Locator | 8
GRIFFITHS, Ashley | Supervisor | 5 |  |  |  | Greame Tuffloy | Service Locator | 8
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 |  |  |  | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  |  |  |  | Sea Container 20ft | 951200 | 1
[6 empty] | Site Sentry Tower |  | 2
[6 empty] | Skip Bin |  | 1
[6 empty] | Hydrocarbon Bund |  | 1
[6 empty] | Temp Fence |  | 1
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Housekeeping
Hazards Reported: | Nil
Incident Free Days | 9
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Completed Demo of Brick Paving
Delap Survey Inspected 9 Properties
Ongoing Survice Location
PHOTOS

## 006
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-12
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 6 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 33 degrees Wind: 25 km/h NE Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager | 0 |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10
GRIFFITHS, Ashley | Supervisor | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 |  |  |  | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  |  |  |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 03 | 4 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 2 |  |  |  | Skip Bin |  | 1
[6 empty] | Hydrocarbon Bund |  | 1
[6 empty] | Temp Fence |  | 1
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Loading and Unloading Plant
Hazards Reported: | Nil
Incident Free Days | 10
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Commence Vegetation Strip to basin
Mobilsed Watercart
Mobilisation of Posi Track
PHOTOS
#VALUE!

## 007
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-13
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 7 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 31 degrees Wind: 25 km/h E Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager | 0 |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10
GRIFFITHS, Ashley | Supervisor | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 1 |  |  |  | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  |  |  |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 03 | 3 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
[6 empty] | Hydrocarbon Bund |  | 1
[6 empty] | Temp Fence |  | 1
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Fitness for Work
Hazards Reported: | Nil
Incident Free Days | 11
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Commence Basin Topsoil Strip
PHOTOS
#VALUE!

## 008
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-14
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 8 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 27 degrees Wind: 24 km/h E Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager | 10 |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10
GRIFFITHS, Ashley | Supervisor | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 |  |  |  | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  |  |  |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 03 | 2 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 6 |  |  |  | Skip Bin |  | 1
[6 empty] | Hydrocarbon Bund |  | 1
[6 empty] | Temp Fence |  | 1
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Vehicles
Hazards Reported: | Nil
Incident Free Days | 12
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Complete Basin Topsoil Strip
Commence General Site Vegetation Strip
Fortnightly Progress Meeting
Meet with Maritime Museum and confirmed vibration monitor location
Drainage Order Placed
PHOTOS

## 009
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-15
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 9 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 28 degrees Wind: 25 km/h E Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Katrine Dodd | Cultural Spotter | 1
GRIFFITHS, Ashley | Supervisor | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 2 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 2 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 2 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 | 1 |  |  |  | Temp Fence |  | 1
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | SIMOPS | [7 empty] | 14
Hazards Reported: | Nil
Incident Free Days | 13
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing General Site Vegetation Strip
Yamaji Southern Corporation Onsite
Hard Barracading Onsite
Vibration Monitor Onsite
Gluon onsite
Unknown Footing/ Pole discovered in ground
PHOTOS

## 010
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-16
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 10 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 28 degrees Wind: 21 km/h E Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 9
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Jayden Brecz | Service Locator | 8
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Greame Tuffloy | Service Locator | 8
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 2 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 3 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 | 4 |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Loading and unloading
Hazards Reported: | Nil
Incident Free Days | 14
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Geotech Consulant Engaged
Additional local sand sources explored
Smooth Drum/ Padfoot onsite
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Basecourse for access track onsite
Ongoing Vegetation Strip
Service location forrest street
Additional Temp Fencing onsite
PHOTOS

## 011
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-19
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 11 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 26 degrees Wind: 29 km/h N Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Tody Crossdale | Consultant | 1
[6 empty] | Greg Hipple | Asbestos Consult | 1
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 4 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 4 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 4 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 | 1 |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Asbestos Encountered in Soul Café Crossing
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Barracading/ Public Interaction
Hazards Reported: | Nil
Incident Free Days | 15
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Topsoil Strip inspected by Structerre-Potential issue identified with existing gravel carpark tbc
Potential Asbestos found onsite
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Commence Soul Café Crossing Works dsirupted by found asbestos
Detailed topsoil strip in conjunction with Structerre Consultant
PHOTOS

## 012
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-20
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 12 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 22 km/h N Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Greg Hipple | Asbestos Consult | 3
[6 empty] | Jachai Griffiths | Operator | 10
[6 empty] | Skyline Services Setup Team | Grader Setup | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 5 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 | 2 |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 2
Grader | SLS01 | 8
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Barracading/ Public Interaction (Reinforced)
Hazards Reported: | Nil
Incident Free Days | 16
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Topsoil Strip inspected by Structerre-Potential issue identified with existing gravel carpark tbc
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Seived Soil and Removed Asbestos from Soul Café Crossing
Completed Soul Café Crossing Works
First Delivery of Concrete Pipes onsite
Dug test pits in gravel area to establish gravel thicknesses
PHOTOS

## 013
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-21
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 13 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 22 km/h N Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
GRIFFITHS, Ashley | Supervisor | 4 |  |  |  | Daniel McAuffile | Operator | 10
[6 empty] | Jachai Griffiths | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 1 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 | 5 |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Grader | SLS01 | 9
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Plant on Plant interaction
Hazards Reported: | Nil
Incident Free Days | 17
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Potential issue identified with existing gravel carpark tbc
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Conducted Vibration Trials-Further investigation required on low vibration rolling, High Vibration Rolling to no longer be implemented
Removal of Stripped Vegetation
Commenced Exposure of basecourse in northern lots
Placed Fencing to Forrest Road
Proof Rolling to Lot 118 (Static Compaction only)
Initial Feedback Provided on APRA
Soul café Crossing Open to Public
Survey pick up of stripped area/ basecourse contaminated areas
PHOTOS

## 014
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-22
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 14 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 22 km/h N Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Daniel McAuffile | Operator | 10
[6 empty] | Jachai Griffiths | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 | 10 |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Positve Comms
Hazards Reported: | Nil
Incident Free Days | 18
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Potential issue identified with existing gravel carpark tbc
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Removal of Stripped Vegetation
Removal/ Exposure of Basecourse in Northern Lots
Approval of Keith Gregory Sand
Ongoing APRA Feedback
Fence Removal Forrest Street Side
PHOTOS

## 015
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-23
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 15 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 21 degrees Wind: 16 km/h N Precip: 3mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 8 |  |  |  | Laurent Levy | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Daniel McAuffile | Operator | 10
[6 empty] | Jachai Griffiths | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 5 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 | 10 |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 8
Grader | SLS01 | 10
#VALUE!
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Working around excavations
Hazards Reported: | Nil
Incident Free Days | 19
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Potential issue identified with existing gravel carpark tbc
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
NDM of Foundation to Northern Lots
Mixing of basecourse with won clean material in Northern Lots
Commence Pit Installs to Museum Place Line
Ongoing APRA Feedback
Production affected by Rain
PHOTOS

## 016
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-26
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 17 | [5 empty] | Finish: | 16:00
WEATHER & GROUND CONDITIONS
Temperature: 21 degrees Wind: 16 km/h N Precip: 0.6mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Daniel McAuffile | Operator | 10
LOW, June | HSET | 10 |  |  |  | Jachai Griffiths | Operator
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 9 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 8
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Postive Comms
Hazards Reported: | Nil
Incident Free Days | 20
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Potential issue identified with existing gravel carpark tbc
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing mixing of basecourse with clean won material
Commence Excavation of 300mm Drainage Lines
Discovery of old sewer line not on DBYD
PHOTOS

## 017
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-27
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 17 | [5 empty] | Finish: | 16:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 15 km/h N Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Daniel McAuffile | Operator | 10
LOW, June | HSET | 10 |  |  |  | Jachai Griffiths | Operator
[6 empty] | O'Brian, Jamie | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Plant on Plant Interaction
Hazards Reported: | Nil
Incident Free Days | 21
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Potential issue identified with existing gravel carpark tbc
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing mixing of basecourse with clean won material
Laying of Pipe into Western Culverts
TCD internal HSE audit Commenced
PHOTOS

## 018
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-28
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 18 | [5 empty] | Finish: | 16:00
WEATHER & GROUND CONDITIONS
Temperature: 27 degrees Wind: 33 km/h W Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Daniel McAuffile | Operator | 10
LOW, June | HSET | 10 |  |  |  | Jachai Griffiths | Operator
[6 empty] | O'Brian, Jamie | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Lifting
Hazards Reported: | Nil
Incident Free Days | 22
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Potential issue identified with existing gravel carpark tbc
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing mixing of basecourse with clean won material
Ongoing Excavation of Northern Culvert Lines
Progress Meeting Onsite
Asbestos Discovered in Northern Lots
TCD internal HSE audit ongoing
PHOTOS

## 019
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-29
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 19 | [5 empty] | Finish: | 16:00
WEATHER & GROUND CONDITIONS
Temperature: 25 degrees Wind: 29 km/h SW Precip: 2mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Daniel McAuffile | Operator | 10
LOW, June | HSET | 10 |  |  |  | Jachai Griffiths | Operator
[6 empty] | O'Brian, Jamie | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 7 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Asbestos
Hazards Reported: | Nil
Incident Free Days | 23
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Potential issue identified with existing gravel carpark tbc
Basecourse Identified in Lot 119
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing mixing of basecourse with clean won material
Ongoing Placement of Liners and Pipework in Trench
Asbestos Removed in Northern Lots
TCD internal HSE audit Complete
PHOTOS

## 020
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-30
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 20 | [5 empty] | Finish: | 16:00
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 21 km/h S Precip: 16mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 8
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 8
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Daniel McAuffile | Operator | 8
LOW, June | HSET |  |  |  |  | Jachai Griffiths | Operator
[6 empty] | O'Brian, Jamie | Operator | 8
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 5 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Grader | SLS01 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Asbestos
Hazards Reported: | Nil
Incident Free Days | 23
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Potential issue identified with existing gravel carpark tbc
Rain Affected Day Minimal Production
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Mudding of Pits
Grader Works Stopped to prevent worsening of site conditions
PHOTOS

## 021
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-05-31
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 21 | [5 empty] | Finish: | 16:00
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 15 km/h S Precip: 0.2mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Daniel McAuffile | Operator | 6
LOW, June | HSET |  |  |  |  | Jachai Griffiths | Operator
[6 empty] | O'Brian, Jamie | Operator
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 2 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Grader | SLS01 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | JHA
TCD - Daily Safety Focus: | Asbestos
Hazards Reported: | Nil
Incident Free Days | 23
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Potential issue identified with existing gravel carpark tbc
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Boxout of Road
Grader Works Stopped to prevent worsening of site conditions
Review Barracading for Long Weekend
PHOTOS

## 022
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-03
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 22 | [5 empty] | Finish: | 17:30
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 61 km/h NW Precip: 37.6mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10.5
GRIFFITHS, Daniel | Project Manager | 10.5 |  |  |  | Laurent Levy | Operator | 10.5
GRIFFITHS, Ashley | Supervisor | 10.5 |  |  |  | Daniel McAuffile | Operator | 10.5
LOW, June | HSET |  |  |  |  | Jachai Griffiths | Operator
[6 empty] | O'Brian, Jamie | Operator | 10.5
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 8 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 6 | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 8 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Grader | SLS01 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Wet Weather Controls
Hazards Reported: | Nil
Incident Free Days | 24
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Potential issue identified with existing gravel carpark tbc
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Complete Boxout of basecourse in Lot 119
Grader Works Stopped to prevent worsening of site conditions
Unable to continue with grader works in northern lots due to wet weather
Unable to commence carpark wroks due to wet weather
Commence Backfill of drainage lines
Trial Pad Completed
PHOTOS

## 023
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-04
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 23 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 35 km/h NW Precip: 20.4mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 11 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 8 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 | 10 |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 0
Grader | SLS01 | 0
0 | Repairs Required |  | N/A
1 | Scheduled Service |  | Grader
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Plant on Plant
Hazards Reported: | Nil
Incident Free Days | 25
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Potential issue identified with existing gravel carpark tbc
Grader Offline for Service while limited work fronts are available
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Loader Blend of Basecourse with Fill Material Lot 119
Grader Works Stopped to prevent worsening of site conditions
Trial pad results back methodology to follow
Unable to commence carpark works due to wet weather
Ongoing Excavation to Northern Drainage Line
Removal of Vegitation and Waste from Site
PHOTOS

## 024
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-05
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 24 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 37 km/h S Precip: 8 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 8 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 | 10 |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 0
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
1 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Plant on Plant Interaction
Hazards Reported: | Nil
Incident Free Days | 26
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Potential issue identified with existing gravel carpark tbc
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Mix material to Eastern Boundary Northern Lots
Laying of Drainage Line Northerns Lots
Minor Hydrocarbon. Cleaned up waste to be taken off site in Hydrocarbon IBC at the end of project
PHOTOS

## 025
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-06
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 25 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind: 39 km/h E Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 4 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Grader | SLS01 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
1 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Seatbelts
Hazards Reported: | Nil
Incident Free Days | 27
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Basecourse Cleared From Lot Boundary
CoGG Onsite to Inpsect Drainage
Watercorp Startup Meeting/ Working Near Sewer Pressure Main discussion onsite
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Rolled Mixed Material and Level Lots 119
Drainage Installation Northern Line
NDM Testing to Northern Lots and Lot 199
Conditioned basecouse for
PHOTOS

## 026
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-09
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 26 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 26 degrees Wind: 43 km/h NE Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 5 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
1 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Issues with existing basecourse in lots identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Control of Vehicle Movement
Hazards Reported: | Nil
Incident Free Days | 28
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Basecourse Cleared From Lot Boundary
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Compaction Test Results to lot 119 and mixed material returned conforming
Backfill Drainage line to Northern Lots
Placement of fill to Northern Lots Approx 500t installed
PHOTOS

## 027
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-10
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 27 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 44 km/h WSW Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Truck Movements Internal
Hazards Reported: | Nil
Incident Free Days | 29
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Placement of fill to Northern Lots
Ongoing Backfill of Trenches
PHOTOS

## 028
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-11
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 28 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 21 degrees Wind: 28 km/h E Precip: 0.4mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Truck Movements Internal
Hazards Reported: | Nil
Incident Free Days | 29
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
Progress Meeting
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Placement of fill to Northern Lots
Drainage Patching
PHOTOS

## 029
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-12
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 29 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 21 degrees Wind: 33 km/h NE Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET | 10 |  |  |  | O'Brian, Jamie | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 5 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Truck Movements Internal
Hazards Reported: | Nil
Incident Free Days | 30
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Placement of fill to Northern Lots
Carpark Repairs
PHOTOS

## 031
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-14
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 31 | [5 empty] | Finish: | 15:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 24 km/h W Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer
GRIFFITHS, Daniel | Project Manager |  |  |  |  | Laurent Levy | Operator | 8
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator
GRIFFITHS, Ashley | Supervisor | 9 |  |  |  | Jachai Griffiths | Operator | 8
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 8 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 5 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Grader | SLS01
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Removed Fence to Northern Lots Installed Temp Fence Test Pitted Area for Gravel
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 32
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Placement of fill to Northern Lots
Carpark Repairs Patch Holes near Station Platform
PHOTOS

## 032
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-16
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 33 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 30 km/h NE Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager |  |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 33
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Placement of fill to Northern Lots
Commence Excavation of Gravel to Northern Lots Strip
Removal of Dust Fence
PHOTOS

## 033
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-17
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 33 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 48 km/h N Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Plant on Plant
Hazards Reported: | Nil
Incident Free Days | 34
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Placement of fill to Northern Lots
Breaking up of gravel along Fenceline
PHOTOS

## 034
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-18
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 34 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 61 km/h N Precip: 31.6mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Public Interaction
Hazards Reported: | Nil
Incident Free Days | 35
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Placement of fill to Northern Lots
Foundation Prep Along Fence
Sump Works
Locate Joints of SPM
PHOTOS

## 035
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-19
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 35 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 30 km/h N Precip: 0.6mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Plant on Plant Interaction
Hazards Reported: | Nil
Incident Free Days | 36
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Placement of fill to Northern Lots
Power Startup Meeting
Location of Addional Services
Patching Drainage lines
PHOTOS

## 036
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-20
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 36 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 67 km/h N Precip: 8mm (Geraldton Airport)
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 6
GRIFFITHS, Daniel | Project Manager | 8 |  |  |  | Laurent Levy | Operator | 6
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 6
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 6
[6 empty] | Rixon, Ian | Operator | 6
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 6
Grader | SLS01 | 6
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Truck Routes Onsite
Hazards Reported: | Nil
Incident Free Days | 37
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
Works Stopped Early Due to Heavy Rain
APRA Signed
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Placement of fill to Northern Lots
Watercorp Pipelaying Course
Rocking Drainge Sump
PHOTOS

## 037
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-23
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 37 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 41 km/h SE Precip: 3.4mm (31mm encountered over the weekend
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Managing Weather
Hazards Reported: | Nil
Incident Free Days | 38
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
No worksover the weekend due to weather
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Import Fill to Lot 199 and Verges
Mitigating Water to allow trucks to safely passage through site
PHOTOS

## 038
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-24
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 38 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 18 degrees Wind: 44 km/h SE Precip: 0.2 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Managing Weather
Hazards Reported: | Nil
Incident Free Days | 38
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Import Fill to Lot 199 and Verges
PHOTOS

## 039
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-25
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 39 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 20 degrees Wind: 35 km/h NE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Plant on Plant interaction
Hazards Reported: | Nil
Incident Free Days | 40
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
Progress Meeting
Meet with watercorp to discuss shutdown-Potential shutdown days to be confirmed. Costs to be completed by WC
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Import Fill to Lot 199 and Verges
Fencing to Baily Street End
Inspect pressure main to confirm diameter of pipe
Sweeping of intersection
PHOTOS

## 040
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-26
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 40 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 21 degrees Wind: 22 km/h NE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 3 | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 5 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 7
Grader | SLS01 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Plant on Plant
Hazards Reported: | Nil
Incident Free Days | 40
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Import Fill to 119 and verges
Commenced placement of fill to laneway
Filled in old soakwell to road enterance
Sweeping of intersection
PHOTOS

## 041
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-27
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 41 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 39 km/h NE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 5 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 7
Positrak SSL | SSL08 | 5
Grader | SLS01 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Unloading Trucks
Hazards Reported: | Nil
Incident Free Days | 42
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Import Fill to 119 and verges
Ongoing Fill to Laneway
Commence excavation power trenching
Sweeping of intersection
Delivery of Power and Water Materials
Remove fecning to foreshore drive
Demolish paving to Bailey Street Access
All service now found
PHOTOS

## 042
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-06-30
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 42 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind: 26 km/h NE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Safe Driving
TCD - Daily Safety Focus: | Trenching
Hazards Reported: | Nil
Incident Free Days | 43
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Import Fill to verges
NDM of Laneway and Lot 119
Ongoing Underground Excavation and Pipe Backfill
Removal of Asphalt Material
PHOTOS

## 043
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-01
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 43 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind: 26 km/h NE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Barracading
Hazards Reported: | Nil
Incident Free Days | 43
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Import Fill to verges
Ongoing Underground Excavation and Pipe Backfill
Transport of Ballast Material to site nominated by client
Ongoing Removal of Ballast and backfill with sand
PHOTOS

## 044
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-02
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 44 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 3 km/h WSW Precip: 0.6 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Barracading
Hazards Reported: | Nil
Incident Free Days | 43
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Import Fill to verges
Ongoing Underground Excavation and Pipe Backfill
Transport of Ballast Material to site nominated by client
Met with WC onsite to discuss caison methodology and inspect SPM crossings
Ongoing Removal of Ballast to Norht of Sump
PHOTOS

## 045
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-03
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 45 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind: 56 km/h WSW Precip: 16 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 3
Positrak SSL | SSL08 | 10
Grader | SLS01
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Watercorp unable to provide pressure main shut down 5/7/25
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 47
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
Rain Affected Day
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Import Fill to verges
Ongoing Underground Excavation and Pipe Backfill
Commence Caisson at Forrest Street End
Gas Startup Meeting Took Place
PHOTOS

## 046
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-04
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 46 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 20 degrees Wind: 43 km/h SSW Precip: 2.4 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 9
[6 empty] | Rixon, Ian | Operator | 9
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 5 | 6 Wheel Tipper | AMG04 | 1 | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 3
Positrak SSL | SSL08 | 10
Grader | SLS01
1.5 Excavator | AMG 009 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Watercorp unable to provide pressure main shut down 5/7/25
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 47
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-01 Implemented
Rain Affected Day
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Trimming of Batters
Ongoing Underground Excavation and Pipe Backfill
Completion of Caisson Works Forrest Street
Gas Materials and Irrigation Sleeves onsite
PHOTOS

## 047
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-07
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 46 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 20 degrees Wind: 69 km/h WSW Precip: 8.6 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 5
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 5
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator
[6 empty] | Rixon, Ian | Operator
[6 empty] | Goodwin, Noah | Labourer | 8
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 3 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 2
Grader | SLS01
1.5 Excavator | AMG 009 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Watercorp unable to provide pressure main shut down 5/7/25
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Plant on Plant Interaction
Hazards Reported: | Nil
Incident Free Days | 49
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
Rain Affected Day
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Underground Excavation and Pipe Backfill
Backfill Restricted due to rain
PHOTOS

## 048
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-08
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 48 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 18 degrees Wind: 28 km/h ENE Precip: 0.2 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 9.5
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 9.5
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET | 10 |  |  |  | O'Brian, Jamie | Operator
[6 empty] | Rixon, Ian | Operator
[6 empty] | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter | 8
[6 empty] | Mounsey, Matt | Gas Fitter | 8
[6 empty] | Herring, Levin | Gas Fitter | 8
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 8
Grader | SLS01
1.5 Excavator | AMG 009 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Watercorp unable to provide pressure main shut down 5/7/25
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Plant on Plant Interaction
Hazards Reported: | Nil
Incident Free Days | 50
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Underground Excavation and Pipe Backfill
Fencing of Foreshore Drive for museum place intersection
Gas Laying Commenced
PHOTOS

## 049
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-09
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 49 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 18 degrees Wind: 39 km/h ESE Precip: 0.4 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET | 10 |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
[6 empty] | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 5
Grader | SLS01
1.5 Excavator | AMG 009 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Watercorp unable to provide pressure main shut down 5/7/25
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 51
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Installed temp fencing to foreshire drive footpath
Ongoing underground services
PHOTOS

## 050
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-10
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 50 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 35 km/h E Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 8
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 8
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 8
[6 empty] | Goodwin, Noah | Labourer | 8
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 5
Grader | SLS01
1.5 Excavator | AMG 009 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Watercorp unable to provide pressure main shut down 5/7/25
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Plant on Plant
Hazards Reported: | Nil
Incident Free Days | 52
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Installed temp fencing to foreshire drive footpath
Ongoing underground services
Commenced Drainage to 525 Line
PHOTOS

## 051
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-11
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 51 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 20 degrees Wind: 33 km/h NNE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 8
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 8
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 8
[6 empty] | Goodwin, Noah | Labourer | 8
[6 empty] | Chester, Matt | Gas Fitter | 5
[6 empty] | Mounsey, Matt | Gas Fitter | 5
[6 empty] | Herring, Levin | Gas Fitter | 5
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 5
Grader | SLS01
5t Excavator | AMG 007 | 7
1.5 Excavator | AMG 009 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New irrigation design received
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Working in Trenches
Hazards Reported: | Nil
Incident Free Days | 53
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground services
Ongoing Drainage to 525 Line
Preparation to watercorp shut down
PHOTOS

## 052
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-12
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 52 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 20 degrees Wind: 28 km/h SW Precip: 2 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 8
GRIFFITHS, Daniel | Project Manager |  |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 8
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator
[6 empty] | Rixon, Ian | Operator | 8
[6 empty] | Goodwin, Noah | Labourer | 8
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 5
Grader | SLS01
5t Excavator | AMG 007 | 7
1.5 Excavator | AMG 009 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
APRA Shutdown
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | APRA Works
Hazards Reported: | Nil
Incident Free Days | 54
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground services
Passed 525 and 600 Pipe Beneath sewer pressure main
PHOTOS

## 053
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-14
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 53 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 61 km/h SW Precip: 2.8 (6.4mm Sunday) mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
[6 empty] | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 10
Grader | SLS01
5t Excavator | AMG 007 | 10
1.5 Excavator | AMG 009 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
APRA Shutdown
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Simops
Hazards Reported: | Nil
Incident Free Days | 55
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground services
Complete 525 Culvert (Extend into Future Area)
PHOTOS

## 054
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-15
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 54 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 18 degrees Wind 22 km/h SW Precip: 0.2 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
[6 empty] | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 2 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 5
Grader | SLS01
5t Excavator | AMG 007 | 10
1.5 Excavator | AMG 009
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Working in Trenches
Hazards Reported: | Nil
Incident Free Days | 56
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground services
Commenced digging 600 crossing encountered potential clash with existing deep drainage line
PHOTOS

## 055
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-16
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 55 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 18 degrees Wind 22 km/h SW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
[6 empty] | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 3 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 5
Grader | SLS01
5t Excavator | AMG 007 | 10
1.5 Excavator | AMG 009
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Working in Trenches
Hazards Reported: | Nil
Incident Free Days | 56
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground services
Commenced digging 300 crossing
Surveyed existing deep stormwater to confirm clash Issue
3E onsite for electrical inspection
PHOTOS

## 056
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-17
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 56 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind 28 km/h S Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
[6 empty] | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 3 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 5
Grader | SLS01
5t Excavator | AMG 007 | 10
1.5 Excavator | AMG 009
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Seatbelts and Driving on Site
Hazards Reported: | Nil
Incident Free Days | 58
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
Meeting with COGG Traffic Manager undertaken 17/7/25 working through solutions for foreshore drive
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground services
Laying of Pipework to 300 crossing (COGG Inspected)
Completed digging 600 crossing trench
PHOTOS

## 057
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-18
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 57 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 20 degrees Wind 31 km/h S Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
[6 empty] | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 8 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 3 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 8
Grader | SLS01
5t Excavator | AMG 007 | 10
1.5 Excavator | AMG 009 | 8
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Diriving onsite
Hazards Reported: | Nil
Incident Free Days | 59
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground services-Connections to New
Backfill 300 Drainage Crossing
Lay Pipes to 600 Crossing Inspected by COGG
PHOTOS

## 058
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-19
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 58 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 20 degrees Wind 28 km/h NNE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer
GRIFFITHS, Daniel | Project Manager |  |  |  |  | Laurent Levy | Operator | 8
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator
GRIFFITHS, Ashley | Supervisor | 8 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 8
[6 empty] | Rixon, Ian | Operator
[6 empty] | Goodwin, Noah | Labourer | 8
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 5 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 5 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 5
Grader | SLS01
5t Excavator | AMG 007 | 5
1.5 Excavator | AMG 009
5t Excavator | AA 25 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Working in Trenches
Hazards Reported: | Nil
Incident Free Days | 60
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Sewer Connection
Backfill 600 Drainage Crossing
PHOTOS

## 059
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-21
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 59 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 16 degrees Wind 80 km/h SSW Precip: 9 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
Skinner, JAMIE | Supervisor | 10 |  |  |  | Rixon, Ian | Operator
[6 empty] | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 3 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 5 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 5
Grader | SLS01
5t Excavator | AMG 007 | 10
1.5 Excavator | AMG 009 | 5
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Working in Trenches
Hazards Reported: | Nil
Incident Free Days | 60
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Sewer Connection
Backfill 600 Drainage Crossing
PHOTOS

## 060
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-22
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 60 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 18 degrees Wind 28 km/h NNE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET | 10 |  |  |  | O'Brian, Jamie | Operator | 10
Skinner, JAMIE | Supervisor | 11 |  |  |  | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 2 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 2
Positrak SSL | SSL08 | 10
Grader | SLS01
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 2
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Slips Trips and Falls
Hazards Reported: | Nil
Incident Free Days | 62
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Underground Services
Ongoing Drainge Forrest Street Section Inspected by COGG
PHOTOS

## 061
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-23
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 61 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 18 degrees Wind 28 km/h NNE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET | 10 |  |  |  | O'Brian, Jamie | Operator | 10
Skinner, JAMIE | Supervisor | 11 |  |  |  | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 2 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 2
Positrak SSL | SSL08 | 10
Grader | SLS01
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 2
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | PPE
Hazards Reported: | Nil
Incident Free Days | 63
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
Progress Meeting
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Underground Services
Ongoing Drainge Forrest Street Section Inspected by COGG
Setting of lids to forrest street
PHOTOS

## 062
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-24
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 62 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 16 degrees Wind 69 km/h SW Precip: 38.2 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
Skinner, JAMIE | Supervisor | 11 |  |  |  | Goodwin, Noah | Labourer
[6 empty] | Chester, Matt | Gas Fitter | 5
[6 empty] | Mounsey, Matt | Gas Fitter | 5
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 2 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 2
Positrak SSL | SSL08 | 10
Grader | SLS01
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 2
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | PPE
Hazards Reported: | Nil
Incident Free Days | 64
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
Rain Affected Day
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Underground Services
Completed backfill of drainage to forrest street
Sink Holes to southern side of site investigated and backfilled
Commenced Cutting of pits for lids
PHOTOS

## 063
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-25
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 63 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 15 degrees Wind E 35km/h SW Precip: 0.4 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
Skinner, JAMIE | Supervisor | 12 |  |  |  | Goodwin, Noah | Labourer
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 1 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 10
Grader | SLS01
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 5
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Driving on site
Hazards Reported: | Nil
Incident Free Days | 65
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Underground Services
Completed backfill of drainage to forrest street
Installation of irrigation sleeves
Ongoing Cutting for Lids to drainage pids
PHOTOS

## 064
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-26
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 63 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 17 degrees Wind 33km/h NE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 9
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 7
GRIFFITHS, Ashley | Supervisor | 9 |  |  |  | Jachai Griffiths | Operator | 9
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 7
Skinner, JAMIE | Supervisor |  |  |  |  | Goodwin, Noah | Labourer
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 3 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 4 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08
Grader | SLS01
5t Excavator | AMG 007
1.5 Excavator | AMG 009
5t Excavator | AA 25 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Working around Trenches
Hazards Reported: | Nil
Incident Free Days | 66
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Backfilling of Underground Services
Removal of Rubbish
Install 1 irrigation sleeve
PHOTOS

## 065
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-28
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 65 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 15 degrees Wind 78km/h SE Precip: 22.2 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
SKINNER, Jamie | Supervisor | 10 |  |  |  | Goodwin, Noah | Labourer
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08
Grader | SLS01
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 5
5t Excavator | AA 25 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Re-establishing site
Hazards Reported: | Nil
Incident Free Days | 67
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
Rain Affected Day
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Repairs to Site Fencing
Backfill of Underground Services
Ongoing cutting of Drainage lids
PHOTOS

## 066
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-29
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 66 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 15 degrees Wind 17km/h N Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Buecz, Jayden | Driller | 8
SKINNER, Jamie | Supervisor | 10 |  |  |  | Anderson, Peter | Driller | 8
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 5
Grader | SLS01
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 5
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Working Around Trenches
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
Site still heavily affected by rain
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Completed Irrigation Sleeves
Backfill of Underground Services
Ongoing Underground Services
Ongoing cutting of Drainage pits
Drillers onsite Baily Street
Commenced Irrigation Mainline
Photos

## 067
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-30
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 67 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind 28km/h E Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Simpson Josh | Operator | 8
SKINNER, Jamie | Supervisor | 10 |  |  |  | Buecz, Jayden | Driller | 8
[6 empty] | Anderson, Peter | Driller | 8
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 5
Grader | SLS01
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 5
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Pulling PE Pipe
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
Site still heavily affected by rain
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Backfill of Underground Services
Ongoing cutting of Drainage pits
Drillers onsite Baily Street
Ongoing Irrigation Mainline
Photos

## 068
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-07-31
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 68 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind 38km/h NNE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Simpson Josh | Operator | 10
SKINNER, Jamie | Supervisor | 10 |  |  |  | Buecz, Jayden | Driller | 8
[6 empty] | Anderson, Peter | Driller | 8
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter | 6
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 8
Positrak SSL | SSL08 | 5
Grader | SLS01 | 8
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 5
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Cutting PE pipe
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Backfill of Underground Services
Ongoing cutting of Drainage pits
Drillers onsite Baily Street
Commenced Subgrade Prep
Photos

## 069
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-01
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 69 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind 52km/h NNE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Simpson, Josh | Operator | 10
SKINNER, Jamie | Supervisor | 10 |  |  |  | Buecz, Jayden | Driller | 8
[6 empty] | Anderson, Peter | Driller | 8
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter | 8
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 8
Positrak SSL | SSL08 | 5
Grader | SLS01 | 8
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 5
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Speaking up
TCD - Daily Safety Focus: | Plant on Plant Interaction
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing cutting of Drainage pits
Drillers onsite Baily Street
Poly Weld Irrigation and construct thrust blocks
Ongoing Subgrade Prep
Photos

## 070
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-04
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 70 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 18 degrees Wind 12 km/h WSW Precip: 0.4mm (15.8mm over the weekend)
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Simpson, Josh | Operator | 10
SKINNER, Jamie | Supervisor | 10 |  |  |  | O'Reilly, James | Operator | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 2 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 6 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Positrak SSL | SSL08 | 6
Grader | SLS01 | 5
5t Excavator | AMG 007
1.5 Excavator | AMG 009
5t Excavator | AA 25 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Speaking up
TCD - Daily Safety Focus: | Plant on Plant Interaction
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing cutting of Drainage pits
Drillers onsite Baily Street
Install Flushing/ Air Valves to Mainline
Rough Set Pits to irrigation mainline
Install headwall in sump
Ongoing Subgrade Prep
Photos

## 071
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-05
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 71 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind 30km/h NE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Simpson, Josh | Operator | 10
SKINNER, Jamie | Supervisor | 10 |  |  |  | O'Reilly, James | Operator | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 5 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Positrak SSL | SSL08 | 6
Grader | SLS01 | 5
5t Excavator | AMG 007
1.5 Excavator | AMG 009
5t Excavator | AA 25 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Speaking up
TCD - Daily Safety Focus: | Lifting
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing cutting of Drainage pits
Construction of Trial Pad
Install Flushing/ Air Valves to Mainline
Pushed Laterals through sleeve
Rough Set Pits to irrigation mainline
Install headwall in sump
Ongoing Subgrade Prep
Photos

## 072
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-06
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 72 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind No reading from BOM km/h N Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Simpson, Josh | Operator | 10
SKINNER, Jamie | Supervisor | 10 |  |  |  | O'Reilly, James | Operator | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 5 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 8 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 6 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Positrak SSL | SSL08 | 5
Grader | SLS01 | 8
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 5
5t Excavator | AA 25 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Porters advised that City of Greater Geraldton have rejected extension of Forrest Street Paving Area to accommodate additional services
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Speaking up
TCD - Daily Safety Focus: | Plant on Plant Interaction
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
Progress Meeting
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground Services
Rebuilding of verges
Placed material for laneway road widening
Ongoing Subgrade Prep
Photos

## 073
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-07
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 73 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind 52km/h N Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Simpson, Josh | Operator | 10
SKINNER, Jamie | Supervisor | 10 |  |  |  | O'Reilly, James | Operator | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 7 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 5 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 8 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 6 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Positrak SSL | SSL08 | 10
Grader | SLS01 | 10
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 5
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Speaking up
TCD - Daily Safety Focus: | Wind and dust
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing cutting of Drainage pits
Denso Tape of water risers (inspected by WC)
Install headwall in sump
Ongoing Subgrade Prep
Photos