## 069
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-01
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 69 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind 52km/h NNE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Simpson, Josh | Operator | 10
SKINNER, Jamie | Supervisor | 10 |  |  |  | Buecz, Jayden | Driller | 8
[6 empty] | Anderson, Peter | Driller | 8
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter | 8
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 8
Positrak SSL | SSL08 | 5
Grader | SLS01 | 8
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 5
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Speaking up
TCD - Daily Safety Focus: | Plant on Plant Interaction
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing cutting of Drainage pits
Drillers onsite Baily Street
Poly Weld Irrigation and construct thrust blocks
Ongoing Subgrade Prep
Photos

## 070
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-04
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 70 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 18 degrees Wind 12 km/h WSW Precip: 0.4mm (15.8mm over the weekend)
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Simpson, Josh | Operator | 10
SKINNER, Jamie | Supervisor | 10 |  |  |  | O'Reilly, James | Operator | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 10 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 2 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 6 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Positrak SSL | SSL08 | 6
Grader | SLS01 | 5
5t Excavator | AMG 007
1.5 Excavator | AMG 009
5t Excavator | AA 25 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Speaking up
TCD - Daily Safety Focus: | Plant on Plant Interaction
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing cutting of Drainage pits
Drillers onsite Baily Street
Install Flushing/ Air Valves to Mainline
Rough Set Pits to irrigation mainline
Install headwall in sump
Ongoing Subgrade Prep
Photos

## 071
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-05
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 71 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind 30km/h NE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Simpson, Josh | Operator | 10
SKINNER, Jamie | Supervisor | 10 |  |  |  | O'Reilly, James | Operator | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 5 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Positrak SSL | SSL08 | 6
Grader | SLS01 | 5
5t Excavator | AMG 007
1.5 Excavator | AMG 009
5t Excavator | AA 25 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Speaking up
TCD - Daily Safety Focus: | Lifting
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing cutting of Drainage pits
Construction of Trial Pad
Install Flushing/ Air Valves to Mainline
Pushed Laterals through sleeve
Rough Set Pits to irrigation mainline
Install headwall in sump
Ongoing Subgrade Prep
Photos

## 072
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-06
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 72 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind No reading from BOM km/h N Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Simpson, Josh | Operator | 10
SKINNER, Jamie | Supervisor | 10 |  |  |  | O'Reilly, James | Operator | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 5 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 8 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 6 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Positrak SSL | SSL08 | 5
Grader | SLS01 | 8
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 5
5t Excavator | AA 25 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Porters advised that City of Greater Geraldton have rejected extension of Forrest Street Paving Area to accommodate additional services
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Speaking up
TCD - Daily Safety Focus: | Plant on Plant Interaction
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground Services
Rebuilding of verges
Placed material for laneway road widening
Ongoing Subgrade Prep
Photos

## 073
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-07
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 73 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind 52km/h N Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | Simpson, Josh | Operator | 10
SKINNER, Jamie | Supervisor | 10 |  |  |  | O'Reilly, James | Operator | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 7 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 5 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 8 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 6 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Positrak SSL | SSL08 | 10
Grader | SLS01 | 10
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 5
5t Excavator | AA 25 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Speaking up
TCD - Daily Safety Focus: | Wind and dust
Hazards Reported: | Nil
Incident Free Days
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing cutting of Drainage pits
Denso Tape of water risers (inspected by WC)
Install headwall in sump
Ongoing Subgrade Prep
Photos

## 074
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-07
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 74 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 61 km/h SW Precip: 2.8 (6.4mm Sunday) mm | [8 empty] | N/A
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
[6 empty] | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 10
Grader | SLS01
5t Excavator | AMG 007 | 10
1.5 Excavator | AMG 009 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
APRA Shutdown
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Simops
Hazards Reported: | Nil
Incident Free Days | 55
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground services
Complete 525 Culvert (Extend into Future Area)
PHOTOS

## 075
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-08
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 75 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 61 km/h SW Precip: 2.8 (6.4mm Sunday) mm | [8 empty] | 0.0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
[6 empty] | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 10
Grader | SLS01
5t Excavator | AMG 007 | 10
1.5 Excavator | AMG 009 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
APRA Shutdown
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Simops
Hazards Reported: | Nil
Incident Free Days | 55
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground services
Complete 525 Culvert (Extend into Future Area)
PHOTOS

## 076
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-09
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 76 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 61 km/h SW Precip: 2.8 (6.4mm Sunday) mm | [8 empty] | 0.0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator | 10
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
[6 empty] | Rixon, Ian | Operator | 10
[6 empty] | Goodwin, Noah | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 10
Grader | SLS01
5t Excavator | AMG 007 | 10
1.5 Excavator | AMG 009 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
APRA Shutdown
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Simops
Hazards Reported: | Nil
Incident Free Days | 55
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground services
Complete 525 Culvert (Extend into Future Area)
PHOTOS

## 077
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-11
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 7:00
Report Number: | 77 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 18 km/h SW Precip: 0
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
SKINNER,JAMIE | Supervisor | 11.5 |  |  |  | O'Reilly,James | Operator | 10
[6 empty] | Simpson,Joshua | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor | 2
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | LD-011 | 10 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | A1-109 | 1 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 5 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Positrak SSL | SSL08 | 10
Grader | SLS01 | 10
5t Excavator | AMG 007
1.5 Excavator | AMG 009 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours: |  | 39
DELAYS-OPPORTUNITY
Awaiting Detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street Awaiting Feedback on Batters Treatment
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Simops
Hazards Reported: | Nil
Incident Free Days | 77
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
COGG Inspected Subgrade 2:30
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing underground services Bayly st end - Water/gas/power install
Install of Coms pit for future sub-division Ally way widening + verge build up
Subgrade cut and windrow + pick up spoil with Loader
Soil tester onsite to complete supplimentary subgrade soil tests
PHOTOS

## 078
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-12
Project Location: | Geraldton | [5 empty] | Day: | 2025-08-12
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 77 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 25 km/h SW Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 8
GRIFFITHS, Daniel | Project Manager | 11 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 9.5
SKINNER,Jamie | Supervisor | 11 |  |  |  | O'Reilly,James | Operator | 10
[6 empty] | Simpson,Joshua | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor | 2
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | LD-011 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  |  |  |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 10 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 10
Positrak SSL | SSL08 | 5
Grader | SLS01 | 10
5t Excavator | AMG 007 | 5
1.5 Excavator | AMG 009
5t Excavator | AI-106 | 7
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting Detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Speaking Up
TCD - Daily Safety Focus: | Simops
Hazards Reported: | Nil
Incident Free Days | 0
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 1 | Light Pole Struck by positrack Foreshore Drive
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Underground services - Backfilling |  | Commence Cable Jointing
Proof roll test witnessed by COGG at 7:30am |  | Centre-link ramp access boxed out and rolled
Importing of Sub-base material |  | Builiding up verges to design height
Balancing of Sub-base material@Chambers |  | Furniture Ordered
PHOTOS

## 079
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-13
Project Location: | Geraldton | [5 empty] | Day: | 2025-08-13
Project Number: | TCD-1816 | [5 empty] | Start: | 0600AM
Report Number: | 77 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind: 51 km/h SW Precip: 7mm | [8 empty] | 0.0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 9
GRIFFITHS, Daniel | Project Manager | 10 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
SKINNER,JAMIE | SUPERVISOR | 11.5 |  |  |  | Jamie.O'K | Operator | 10
[6 empty] | Simpson,Joshua | Labourer | 0
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor | 2
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 10
Grader | SLS01
5t Excavator | AMG 007 | 10
1.5 Excavator | AMG 009 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting Detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Simops
Hazards Reported: | Nil
Incident Free Days | 0
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
.Underground services - Gas main install and welding |  | .Kiosk/Transformer install and switching
.Final-trimming and rolling off@Chambers |  | .Sub-base placement on centrelink ramp
.Importing of Sub-base material |  | .Building verges up@Lot 118
.Balancing of Sub-base material@Bayly to Forrest street |  | .Soil tested Sub-base 125mm test

## 080
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-14
Project Location: | Geraldton | [5 empty] | Day: | 2025-08-14
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 80 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 43 km/h WSW Precip: 10.2mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10.5
GRIFFITHS, Daniel | Project Manager | 11 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10.5
SKINNER,JAMIE | SUPERVISOR | 11 |  |  |  | O'Reilly,James | Operator | 10
[6 empty] | Simpson,Joshua | Labourer | 10
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor | 2
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 10
Grader | SLS01
5t Excavator | AMG 007 | 10
1.5 Excavator | AMG 009 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting Detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Simops
Hazards Reported: | Nil
Incident Free Days | 1
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
.Underground services - Gas main install and welding |  | .Kiosk/Transformer install and switching
.Lot 119 Gravel 30mm layer- Stock-piling excess |  | .Sub-base placement on centrelink ramp
.Importing of Basecourse material |  | .Widening of Ally-way
.Balancing of Basecourse material@Bayly to Forrest street

## 081
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-15
Project Location: | Geraldton | [5 empty] | Day: | 2025-08-15
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 81 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 18 degrees Wind: 35 km/h E Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer | 10.5
GRIFFITHS, Daniel | Project Manager | 9 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 6 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10.5
SKINNER,JAMIE | SUPERVISOR | 11.5 |  |  |  | O'Reilly,James | Operator
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor | 2
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 10 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 10
Grader | SLS01
5t Excavator | AMG 007 | 10
1.5 Excavator | AMG 009 | 10
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting Detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street Awaiting Feedback on Batters Treatment
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Simops
Hazards Reported: | Nil
Incident Free Days | 2
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
.Balancing of Basecourse material@Bayly to Forrest street |  | .Concreting of Watermain bends
.Rolling Sub-base material
.Trimming pick-ups
.Soil test Basecourse@Bayly to Forrest st
Photos

## 082
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-16
Project Location: | Geraldton | [5 empty] | Day: | Saturday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 82 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind: 44 km/h NE Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer
GRIFFITHS, Daniel | Project Manager | 6 |  |  |  | Laurent Levy | Operator | 6
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 6
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator
SKINNER,Jamie | Supervisor |  |  |  |  | O'Reilly,James | Operator
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 2 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 2 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 3 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 3
Grader | SLS01
5t Excavator | AMG 007
1.5 Excavator | AMG 009
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting Detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street Awaiting Feedback on Batters Treatment
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Bunting and Barracading
Hazards Reported: | Nil
Incident Free Days | 3
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Tidy up and Rebunting of Pits
Concreteing of Bends and compaciton of backfill near Country Builders
Photos

## 083
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-18
Project Location: | Geraldton | [5 empty] | Day: | Saturday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 82 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind: 44 km/h NE Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  |  |  |  | Khegan Brockman | Labourer
GRIFFITHS, Daniel | Project Manager | 6 |  |  |  | Laurent Levy | Operator | 6
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 6
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator
SKINNER,Jamie | Supervisor |  |  |  |  | O'Reilly,James | Operator
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 2 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 2 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 3 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03
Positrak SSL | SSL08 | 3
Grader | SLS01
5t Excavator | AMG 007
1.5 Excavator | AMG 009
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting Detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street Awaiting Feedback on Batters Treatment
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Bunting and Barracading
Hazards Reported: | Nil
Incident Free Days | 3
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Tidy up and Rebunting of Pits
Concreteing of Bends and compaciton of backfill near Country Builders
Photos

## 084
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-18
Project Location: | Geraldton | [5 empty] | Day: | Monday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 82 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind: 44 km/h NE Precip: 23mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 10 | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11.5 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
SKINNER,Jamie | Supervisor |  |  |  |  | Chester, Matt | Gas Fitter | 8
[6 empty] | Mounsey, Matt | Gas Fitter | 8
[6 empty] | Herring, Levin | Gas Fitter
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 5 | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 3 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 4 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 | 10 |  |  |  | Hydrocarbon Bund |  | 1
6 Wheel Tipper | AMG 008 |  |  |  |  | Temp Fence |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 5
Positrak SSL | SSL08 | 3
Grader | SLS01
5t Excavator | AMG 007
1.5 Excavator | AMG 009
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting Detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street Awaiting Feedback on Batters Treatment
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Bunting and Barracading
Hazards Reported: | Nil
Incident Free Days | 4
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
.Cleaning and compacting around New/existing pits. |  | Cutting of Asphalt
.Initial Pressure Test of Gas Main and Irrigation Mainline |  | Completed 1800 High Fencing to Eastern Boundary
Awaiting Compaction Results on Basecourse Layer 1 |  | Forrest street tie-in cut and ready for box out
Photos

## 085
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-19
Project Location: | Geraldton | [5 empty] | Day: | Tuesday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 85 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 56 km/h W Precip: 0mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 10 | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11.5 |  |  |  | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | O'Reilly,James | Operator
[6 empty] | Chester, Matt | Gas Fitter | 4
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor | 2
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 4 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
Mini Tipper | SLS05 | 4 |  |  |  | Temp Fence |  | 1
1 t Excavator | SLS03
Padfoot/ Smooth Drum Roller | RR 03
Multi | 256
Positrak SSL | SSL08 | 5
Grader | SLS01 | 5
5t Excavator | AMG 007
1.5 Excavator | AMG 009
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting Detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street Awaiting Feedback on Batters Treatment
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Take Care Around Key Services
Hazards Reported: | Nil
Incident Free Days | 5
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
.Cleaning and compacting around New/existing pits. |  | .Forrest street tie-in cut and ready for box out
.Trimming Lot batters with grader ready for final with Excavator |  | .Fill up watermain for pressure test
.Irrigation Mainline Pressure Test
Photos

## 086
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-20
Project Location: | Geraldton | [5 empty] | Day: | Wednesday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:30
Report Number: | 86 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 56 km/h SW Precip: 38.8mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 10 | Khegan Brockman | Labourer | 7
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 10 | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | O'Reilly,James | Operator
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 3
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours: | 27
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 4 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
Mini Tipper | SLS05 | 4 |  |  |  | Temp Fence |  | 1
1 t Excavator | SLS03
Padfoot/ Smooth Drum Roller | RR 03
Multi | 256
Positrak SSL | SSL08 | 5
Grader | SLS01 | 5
5t Excavator | AMG 007
1.5 Excavator | AMG 009
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting Detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street Awaiting Feedback on Batters Treatment Major rain damage
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 0
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 1 | Worker reported minor back strain
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
Progress Meeting
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Dewatering Jobsite |  |  | Proof rolling Basecourse Layer 1 Completed and visually inspected by Shire @Chambers,Lot-106 to Forrest street.
Forrest street Tie in Brick pavers removed/Palletised |  |  | Water Main Pressure Testing Witnessed by Glenn Hall
Forrest street Tie in Kerbing removed |  |  | Kerbing/ Blockwork Design Workshopped post progress meeting
Rolling off @Chambers,Forrest to bring moisture to the top
Photos

## 087
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-21
Project Location: | Geraldton | [5 empty] | Day: | Thursday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:30
Report Number: | 87 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 20 degrees Wind: 24 km/h SW Precip: 10.2mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11.5 | Khegan Brockman | Labourer | 10.5
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 11.5 | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer | 10 |  |  |  | Daniel McAuffile | Operator | 10.5
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | O'Reilly,James | Operator
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor | 3
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 4 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
Mini Tipper | SLS05 | 4 |  |  |  | Temp Fence |  | 1
1 t Excavator | SLS03
Padfoot/ Smooth Drum Roller | RR 03
Multi | 256
Positrak SSL | SSL08 | 5
Grader | SLS01 | 5
5t Excavator | AMG 007
1.5 Excavator | AMG 009
1 | Repairs Required |  | Grader Tyre Repaired
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting Detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street . Awaiting Direction on Service Clash Forrest Street Awaiting Feedback on Batters Treatment Minor rain damage Grader down (10am to 12pm)
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 1
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Importing Base-course material |  |  | Trenching power/Coms@Bayly street end
Pushing/Balancing BC @Chambers |  |  | Survey Demo pickup @Bayly + Tap height set-out
Backfilling/Compacting Verges |  |  | Kerbing Markup Issued to PCE
Setting tap heights on Lots and backfilling/Compacting
Photos

## 088
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-22
Project Location: | Geraldton | [5 empty] | Day: | Friday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:30
Report Number: | 88 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 20 degrees Wind: 35km/h E Precip: 0.2 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11 | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 11 | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 10
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | O'Reilly,Sean | Operator | 5
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor
Total Indirect Personnel onsite: | [5 empty] | Total Subcontractor on-site:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel onsite:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 |  |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 4 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
Mini Tipper | SLS05 | 2 |  |  |  | Temp Fence |  | 1
1 t Excavator | SLS03 | 2
Padfoot/ Smooth Drum Roller | RR 03 | 4
Multi | 256 | 4
Positrak SSL | SSL08 | 7
Grader | SLS01 | 6
5t Excavator | AMG 007 | 5
1.5 Excavator | AMG 009 | 3
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting Detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street Awaiting Feedback on Batters Treatment Awaiting Confirmation on Kerbing Design
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Heavy Vehicle Movements
Hazards Reported: | Nil
Incident Free Days | 2
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Pushing/Balancing Base-course @Chambers
Soil test@Chambers BC
Balancing verges Lot-117 to 106
Hauling LV Cable @Bayly street
Photos

## 089
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-23
Project Location: | Geraldton | [5 empty] | Day: | Saturday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 89 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 54 km/h NW Precip: 0.4mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 10 | Khegan Brockman | Labourer
GRIFFITHS, Daniel | Project Manager | 10 | Hanly,Thomas | Operator | 10 | Laurent Levy | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator
SKINNER,Jamie | Supervisor |  |  |  |  | O'Reilly,James | Operator
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 3
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours: | 27
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 4 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 |  |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
Mini Tipper | SLS05 | 4 |  |  |  | Temp Fence |  | 1
1 t Excavator | SLS03
Padfoot/ Smooth Drum Roller | RR 03
Multi | 256
Positrak SSL | SSL08 | 5
Grader | SLS01
5t Excavator | AMG 007
1.5 Excavator | AMG 009
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation of detail on Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street Awaiting Feedback on Batters Treatment
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Fencing and Barracading
Hazards Reported: | Nil
Incident Free Days | 3
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Cleanup of Bayley Street End
Underground Services and Cable Pulling Bayley Street End
Re-construction of Wind Affected Fences
Removal of Brickwork Across Bayley Street
Photos

## 090
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-25
Project Location: | Geraldton | [5 empty] | Day: | Monday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 90 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 15 degrees Wind: 78 km/h NE Precip: 9.4mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 10 | Brockman, Khegan | Labourer
GRIFFITHS, Daniel | Project Manager | 11 | Hanly,Thomas | Operator | 10 | Levy, Laurent | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | McAuffile, Daniel | Operator | 1
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator | 1
SKINNER,Jamie | Supervisor |  |  |  |  | O'Reilly,James | Operator
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 3
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours: | 27
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 5 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | SD |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
Mini Tipper | SLS05 | 4 |  |  |  | Temp Fence |  | 1
1 t Excavator | SLS03 | 3
Padfoot/ Smooth Drum Roller | RR 03 | SD
Multi | 256
Positrak SSL | SSL08 | 3
Grader | SLS01 | SD
5t Excavator | AMG 007
1.5 Excavator | AMG 009
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting Crossing Details for Forrest Street Awaiting Direction on Service Clash Forrest Street Awaiting Feedback on Batters Treatment Major rain damage Import of Basecourse Stopped-All staff redirected where possible
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 5
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Rain Affected Day- Minimal Production Site Mostly Stood Down
Reconstruction of Fences
Backfilling of Trenches Bayley Street
Dewatering of Site
Minor Tidy Up Works Bayley Street
Photos

## 091
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-26
Project Location: | Geraldton | [5 empty] | Day: | Tuesday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 91 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 18 degrees Wind: 44 km/h SW Precip: 12.8mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11.5 | Brockman,Khegan | Labourer
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 11.5 | Levy, Laurent | Operator
O"SHEA, John | Senior Project Engineer |  |  |  |  | McAuffile, Daniel | Operator | 5
GRIFFITHS, Ashley | Supervisor | 5 |  |  |  | Griffiths, Jachai | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | O'Reilly,James | Operator
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Mosley,Joshua | Surveyor | 4
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours: | 27
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Watercart | WC04 | SD |  |  |  | Site Sentry Tower |  | 2
Mini Tipper | SLS05 | 4 |  |  |  | Skip Bin |  | 1
1 t Excavator | SLS03 | SD |  |  |  | Hydrocarbon Bund |  | 1
Padfoot/ Smooth Drum Roller | RR 03 | SD |  |  |  | Temp Fence |  | 1
Multi Roller | 256
Positrak SSL | SSL08 | 5
Grader | SLS01 | SD
5t Excavator | AMG 007
1.5 Excavator | AMG 009
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting confirmation of Kerbing Plan Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Major rain damage Import of Basecourse Stopped-All staff redirected where possible Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile"
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Bunting and Barracading
Hazards Reported: | Nil
Incident Free Days | 6
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
AMG Civil Demobilised
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Removal of kerb@Bayly st Tie-in
Rain Affected Day- Minimal Production Site Mostly Stood Down
Verge build up/Widening for Laterials prep
Survey mark up of Laterial alignment
Tip Run of excess concrete(kerbing)
Photos

## 092
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-27
Project Location: | Geraldton | [5 empty] | Day: | Wednesday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 92 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 18 degrees Wind: 31km/h WSW Precip: 2.2mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11 | Khegan Brockman | Labourer
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 11 | Laurent Levy | Operator
O"SHEA, John | Senior Project Engineer |  |  |  |  | Daniel McAuffile | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Jachai Griffiths | Operator
LOW, June | HSET |  |  |  |  | O'Brian, Jamie | Operator
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | O'Reilly,James | Operator
[6 empty] | Chester, Matt | Gas Fitter
[6 empty] | Mounsey, Matt | Gas Fitter
[6 empty] | Herring, Levin | Gas Fitter
[6 empty] | Dixon, Warren | Irrigation Installer | 4
[6 empty] | Mosley,Joshua | Surveyor | 2
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours: | 27
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 4 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 5 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
Mini Tipper | SLS05 | 4 |  |  |  | Temp Fence |  | 1
1 t Excavator | SLS03
Padfoot/ Smooth Drum Roller | RR 03
Multi Roller | 256
Positrak SSL | SSL08 | 5
Grader | SLS01 | 3
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting confirmation of Kerbing Plan Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Major rain damage Import of Basecourse Stopped-All staff redirected where possible Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile"
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Bunting and Barracading
Hazards Reported: | Nil
Incident Free Days | 7
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Lateral Installations
Rain Affected Day- Minimal Production Site Mostly Stood Down
Rain Affected Day
Photos

## 093
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-28
Project Location: | Geraldton | [5 empty] | Day: | Thursday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 93 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 17 degrees Wind: 31km/h WSW Precip: 1mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11.5 | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 11.5 | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Jachai Griffiths | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | O'Reilly,James | Operator
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | Dixon, Warren | Irrigation Installer | 2
[6 empty] | Mosley,Joshua | Surveyor | 2
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | 6 Wheel Tipper | AMG04 |  | Sea Container 20ft | 951200 | 1
Positrak | AMG 025 | 2 |  |  |  | Site Sentry Tower |  | 2
Watercart | WC04 | 9 |  |  |  | Skip Bin |  | 1
8T Excavator | AMG 014 |  |  |  |  | Hydrocarbon Bund |  | 1
Mini Tipper | SLS05 |  |  |  |  | Temp Fence |  | 1
1 t Excavator | SLS03
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256
Positrak SSL | SSL08 | 5
Grader | SLS01 | 9
5t Excavator | AMG 007
1.5 Excavator | AMG 009
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 | Repairs required but operable |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting Kerbing Plan being Amended by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Import of Basecourse Recommenced Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Simops
Hazards Reported: | Nil
Incident Free Days | 8
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Lateral Trenching and Install
Importing Base-course @ Bayley Lot 106 Heading south
Construction of access track from Bayley to Lot 106 to eliminate contamination
Installation of 100mm sleeve for irrigation underneath concrete ramp
Photos

## 094
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-29
Project Location: | Geraldton | [5 empty] | Day: | Friday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 94 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 37km/h E Precip: 0.2 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11 | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 11 | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Jachai Griffiths | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | O'Reilly,James | Operator
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | Dixon, Warren | Irrigation Installer | 5
[6 empty] | Mosley,Joshua | Surveyor | 2
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  |  |  |  | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 9 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX197 | 2
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01 | 9
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting Kerbing Plan being Amended by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Simops
Hazards Reported: | Nil
Incident Free Days | 9
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Import of Basecourse@Lot 106 heading south
Commence Lateral trenching from@Lot 106 heading south(East side)
Balancing/Compacting Base-course layer@Lot 106 to Forrest st
Solenoid trench open for Box install
Photos

## 095
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-08-30
Project Location: | Geraldton | [5 empty] | Day: | Saturday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 95 | [5 empty] | Finish: | 17:30
WEATHER & GROUND CONDITIONS
Temperature: 21 degrees Wind: 52km/h NE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11 | Khegan Brockman | Labourer
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 11 | Daniel McAuffile | Operator | 6
O"SHEA, John | Senior Project Engineer |  |  |  |  | Jachai Griffiths | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 6
LOW, June | HSET |  |  |  |  | O'Reilly,Sean | Operator | 5
SKINNER,Jamie | Supervisor |  |  |  |  | Dixon, Warren | Irrigation Installer | 5
[6 empty] | Mosley,Joshua | Surveyor | 5
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  |  |  |  | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 10 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX197 | 2
5t Excavator | A118 | 5
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01 | 9
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting Kerbing Plan being Amended by TCD Awaiting Direction on Service Clash Forrest Street-New proposed Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Simops
Hazards Reported: | Nil
Incident Free Days | 10
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Balancing and Rolling of Basecourse
Ongoing Lateral trenching and Install
Photos

## 096
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-01
Project Location: | Geraldton | [5 empty] | Day: | Monday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 96 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 20 degrees Wind: 35km/h S Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11.5 | Brockman, Khegan | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 11.5 | McAuliffe, Daniel | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | O'Brian, Jamie | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Reilly,Sean | Operator | 11
LOW, June | HSET |  |  |  |  | Dixon, Warren | Irrigation Installer | 5
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | Mosley,Joshua | Surveyor | 5
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DAH:400 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 10 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX197 | 3
5t Excavator | A118 | 5
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01 | 9
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting Kerbing Plan being Amended by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Pre-starts
Hazards Reported: | Nil
Incident Free Days | 11
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Irrigation trenching-East side Sump heading South |  |  | Think-water tap into 40mm Comms for solinoids
Irrigation trenching@Lot-106 heading North
Forrest street excess material removal and asphalt box-out
Bayly street Box-out of excess material for sub-grade preperation
Photos

## 097
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-02
Project Location: | Geraldton | [5 empty] | Day: | Tuesday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 97 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 25km/h E Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Brockman, Khegan | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | McAuliffe, Daniel | Operator | 11
O"SHEA, John | Senior Project Engineer |  |  |  |  | O'Brian, Jamie | Operator | 11
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Reilly,Sean | Operator | 12
LOW, June | HSET |  |  |  |  | Dixon, Warren | Irrigation Installer | 5
SKINNER,Jamie | Supervisor | 12 |  |  |  | Mosley,Joshua | Surveyor | 5
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DAH:400 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 10 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS
5t Excavator | A118 | 5
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01 | 9
3 | Repairs Required |  | Steel Drum Roller Broken Belt, Multi Roller Required Jump Start, DPU Starter Motor Replaced
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting Kerbing Plan being Amended by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal COGG Advised they required individual dryback testing testing performed
\
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 12
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
IrrIgation Backfill@East side Lot-106 heading South |  |  | Think-water tap into 40mm Comms for solinoids and box install
IrrIgation trenching@Lot-106 heading North |  |  | Think-water Installation of IrrIgation East side
Final trimming/Balancing Lot 106 heading South
Final trimming/Balancing Chambers Way
Photos

## 098
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-03
Project Location: | Geraldton | [5 empty] | Day: | Wednesday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 94 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind: 25km/h E Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11 | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 11 | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Jachai Griffiths | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | O'Reilly,James | Operator
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | Dixon, Warren | Irrigation Installer
[6 empty] | Mosley,Joshua | Surveyor
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DAH:400 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 10 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01 | 9
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting Kerbing Plan being Amended by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Pre-starts
Hazards Reported: | Nil
Incident Free Days | 11
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
.Irragation garden bed trenching@East side Lot-106 heading South |  |  | .Survey Ascon of entire road surface
.Installation of x2 25mm and x2 50mm sleeves into garden beds
.Irragation garden bed backfilling @Lot-106 heading south
.Final trimming/Balancing @Lot 106-Chambers Way-Forrest
Photos

## 099
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-04
Project Location: | Geraldton | [5 empty] | Day: | Thursday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 94 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind: 25km/h E Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11 | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 11 | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Jachai Griffiths | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | O'Reilly,James | Operator
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | Dixon, Warren | Irrigation Installer
[6 empty] | Mosley,Joshua | Surveyor
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DAH:400 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 10 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01 | 9
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting Kerbing Plan being Amended by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Pre-starts
Hazards Reported: | Nil
Incident Free Days | 11
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
.ITP Proof roll with city sign-off |  | .Laterial install into garden beds@ Bayly street end
.Spray seal and 7mm chip installed and rolled
.Northern lots batter trimming 1:6 batter
.Sub-grade box-out@ Bayly street end
Photos

## 100
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-05
Project Location: | Geraldton | [5 empty] | Day: | Friday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 94 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind: 25km/h E Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11 | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 11 | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Jachai Griffiths | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | O'Reilly,James | Operator
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | Dixon, Warren | Irrigation Installer
[6 empty] | Mosley,Joshua | Surveyor
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DAH:400 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 10 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01 | 9
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting Kerbing Plan being Amended by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Return to Work
TCD - Daily Safety Focus: | Pre-starts
Hazards Reported: | Nil
Incident Free Days | 11
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Photos