## 096
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-01
Project Location: | Geraldton | [5 empty] | Day: | Monday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 96 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 20 degrees Wind: 35km/h S Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11.5 | Brockman, Khegan | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator | 11.5 | McAuliffe, Daniel | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | O'Brian, Jamie | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Reilly,Sean | Operator | 11
LOW, June | HSET |  |  |  |  | Dixon, Warren | Irrigation Installer | 5
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | Mosley,Joshua | Surveyor | 5
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DAH:400 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 10 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX197 | 3
5t Excavator | A118 | 5
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01 | 9
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting Kerbing Plan being Amended by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Pre-starts
Hazards Reported: | Nil
Incident Free Days | 11
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Irrigation trenching-East side Sump heading South |  |  | Think-water tap into 40mm Comms for solinoids
Irrigation trenching@Lot-106 heading North
Forrest street excess material removal and asphalt box-out
Bayly street Box-out of excess material for sub-grade preperation
Photos

## 097
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-02
Project Location: | Geraldton | [5 empty] | Day: | Tuesday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 97 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 25km/h E Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Brockman, Khegan | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | McAuliffe, Daniel | Operator | 11
O"SHEA, John | Senior Project Engineer |  |  |  |  | O'Brian, Jamie | Operator | 11
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Reilly,Sean | Operator | 12
LOW, June | HSET |  |  |  |  | Dixon, Warren | Irrigation Installer | 5
SKINNER,Jamie | Supervisor | 12 |  |  |  | Mosley,Joshua | Surveyor | 5
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DAH:400 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 10 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS
5t Excavator | A118 | 5
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01 | 9
3 | Repairs Required |  | Steel Drum Roller Broken Belt, Multi Roller Required Jump Start, DPU Starter Motor Replaced
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Awaiting COGG confirmation on detail of Centrelink Carpark Awaiting Kerbing Plan being Amended by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal COGG Advised they required individual dryback testing testing performed
\
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 12
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
IrrIgation Backfill@East side Lot-106 heading South |  |  | Think-water tap into 40mm Comms for solinoids and box install
IrrIgation trenching@Lot-106 heading North |  |  | Think-water Installation of IrrIgation East side
Final trimming/Balancing Lot 106 heading South
Final trimming/Balancing Chambers Way
Photos

## 098
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-03
Project Location: | Geraldton | [5 empty] | Day: | Wednesday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 98 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 21 degrees Wind: 46km/h SW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Khegan Brockman | Labourer | 11
GRIFFITHS, Daniel | Project Manager | 12.5 | Hanly,Thomas | Operator | 12 | Daniel McAuffile | Operator | 11
O"SHEA, John | Senior Project Engineer | 12 |  |  |  | Jachai Griffiths | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 11.5
LOW, June | HSET |  |  |  |  | O'Reilly,Sean | Operator | 6
SKINNER,Jamie | Supervisor | 12.5 |  |  |  | Dixon, Warren | Irrigation Installer
[6 empty] | Mosley,Joshua | Surveyor | 6
[6 empty] | Vac Truck | Vacwest | 1
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DAH:400 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 10 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 5
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 5
Positrak SSL | SSL08 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | PositIve Comms
Hazards Reported: | Nil
Incident Free Days | 13
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Installation of x2 25mm and x2 50mm sleeves into garden beds |  |  | Survey Ascon of entire road surface
Irrigation garden bed backfilling @Lot-106 heading south |  |  | Final trimming/Balancing @Lot 106-Chambers Way-Forrest
Photos

## 099
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-04
Project Location: | Geraldton | [5 empty] | Day: | Thursday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 99 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 21 degrees Wind: 33km/h W Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11 | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11 | Hanly,Thomas | Operator | 11 | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer | 11 |  |  |  | Jachai Griffiths | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | O'Reilly,James | Operator
SKINNER,Jamie | Supervisor | 11 |  |  |  | Dixon, Warren | Irrigation Installer
[6 empty] | Mosley,Joshua | Surveyor | 4
[6 empty] | Sealing Crew | Catwest | 6
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DAH:400 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 10 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 8
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 8
Positrak SSL | SSL08 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 14
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Proof roll inspection with COGG |  | Laterial install into garden beds@ Bayly street end
Spray seal and 7mm chip installed and rolled
Northern lots batter trimming 1:6 batter
Sub-grade box-out@ Bayly street end
Photos

## 100
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-05
Project Location: | Geraldton | [5 empty] | Day: | Friday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 100 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 74km/h WE Precip: 4 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11 | Khegan Brockman | Labourer | 5
GRIFFITHS, Daniel | Project Manager | 11 | Hanly,Thomas | Operator |  | Daniel McAuffile | Operator | 5
O"SHEA, John | Senior Project Engineer |  |  |  |  | Jachai Griffiths | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 5
LOW, June | HSET |  |  |  |  | O'Reilly,James | Operator
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | Dixon, Warren | Irrigation Installer
[6 empty] | Mosley,Joshua | Surveyor
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DAH:400 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 |  |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 5
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03
Multi Roller | 256
Positrak SSL | SSL08 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark .Heavy rain event Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Well done and getting bitumen down!
Hazards Reported: | Nil
Incident Free Days | 15
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D impletmented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
.Laterial install into garden beds@ Forrest st end
.Removal of pavers for shut works@ Foreshore
Photos

## 101
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-08
Project Location: | Geraldton | [5 empty] | Day: | Monday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 101 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 17 degrees Wind: 74km/h WE Precip: 6.2 mm (29.6mm over the weekend)
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator |  | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Jachai Griffiths | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | O'Reilly,James | Operator
[6 empty] | Dixon, Warren | Irrigation Installer
[6 empty] | Mosley,Joshua | Surveyor | 4
[6 empty] | Vermeer, Paul | Labourer | 10
[6 empty] | Patroni, Rodney | Labourer | 10
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DAH:400 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 |  |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 5
5t Excavator | A118 | 5
Padfoot/ Smooth Drum Roller | RR 03
Multi Roller | 256
Positrak SSL | SSL08 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD . Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal Demo and new kerb design not aligning awaiting Porters response
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Area awareness
Hazards Reported: | Nil
Incident Free Days | 16
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07B implemented (Closure Notification Upcoming)
Letter Drops to Local Businesses notification of works
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Laterial install into garden beds@ Forrest st - Chambers and Bayly st
Storm-water pit lid setting
Pavers Pre-start meeting
Photos

## 102
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-09
Project Location: | Geraldton | [5 empty] | Day: | Tuesday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 102 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 17 degrees Wind: 23km/h WE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 11.5 | Hanly,Thomas | Operator |  | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  |  |  |  | Jachai Griffiths | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
THOMPSON, Cheryl | HSET | 11.5 |  |  |  | O'Reilly,James | Operator
SKINNER,Jamie | Supervisor | 11.5 |  |  |  | Dixon, Warren | Irrigation Installer | 3
[6 empty] | Mosley,Joshua | Surveyor | 4
[6 empty] | Vermeer, Paul | Labourer | 10
[6 empty] | Patroni, Rodney | Labourer | 10
[6 empty] | Vac Truck | Vac Truck | 6
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DAH:400 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 |  |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 5
5t Excavator | A118 | 10
Padfoot/ Smooth Drum Roller | RR 03
Multi Roller | 256
Positrak SSL | SSL08 | 8
Grader | SLS01
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD . Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal Demo and new kerb design not aligning awaiting Survey report Sump Levels option provided Confirmation of CCTV Alignment Through Crossing Provided
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Lifting
Hazards Reported: | Nil
Incident Free Days | 17
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07B implemented (Closure Notification Upcoming)
TCD Internal Audit Commenced
ATCO Gas Inspected Foreshore Drive Post Service Location
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Setting lids and concrete setting |  | Irrigation Backfill@Centre-link + Country builders
Irrigation trenching@Centre-link section
Pot holing@Foreshore intersection
Photos

## 103
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-10
Project Location: | Geraldton | [5 empty] | Day: | Wednesday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 103 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 21 degrees Wind: 43km/h E Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator |  | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Opetaor | 12 | Jachai Griffiths | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | O'Brian, Jamie | Operator | 10
LOW, June | HSET |  |  |  |  | O'Reilly,James | Operator
SKINNER,Jamie | Supervisor | 12 |  |  |  | Dixon, Warren | Irrigation Installer
TONER, Ultan | Supervisor | 12 |  |  |  | Mosley,Joshua | Surveyor | 5
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | 3 |  |  |  |  | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 |  |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 5 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 5
5t Excavator | A118 | 5
Padfoot/ Smooth Drum Roller | RR 03
Multi Roller | 256
Positrak SSL | SSL08 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD . Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal Demo and new kerb design not aligning awaiting Survey report Sump Levels option provided Confirmation of CCTV Alignment Through Crossing Provided
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 18
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07B implemented (Closure Notification Upcoming)
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Service Exposure |  | Setting of Lids/ Concreting
Surveyor mark-up of Front of kerb
Setting of Storm-water lids/Concreting
Photos

## 104
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-11
Project Location: | Geraldton | [5 empty] | Day: | Thursday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 104 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 39km/h ENE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator |  | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | O'Brian, Jamie | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mosley,Joshua | Surveyor
THOMPSON,Cheryl | HSET
SKINNER,Jamie | Supervisor | 12 |  |  |  | Midwest Kerbing
Ultan,Toner | Supervisor | 12 |  |  |  | Daly,Troy | Specialist | 10
[6 empty] | Kerbers x 3 | Operator/Labourer | 30
[6 empty] | Vac Truck Crew | Operator/Labourer | 10
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 |  |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 5
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03
Multi Roller | 256
Positrak SSL | SSL08 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Demo and new kerb design not aligning awaiting Porters response Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Area awareness
Hazards Reported: | Nil
Incident Free Days | 19
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07B implemented (Closure Notification Upcoming)
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Paving removal @ foreshore contd. |  |  | Kerbers on site to start laying kerbing
Exposure of services to Foreshire Drive West for shut
Waste Removal
Photos

## 105
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-12
Project Location: | Geraldton | [5 empty] | Day: | Friday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 105 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 27 degrees Wind: 48km/h NE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | Khegan Brockman | Labourer | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator |  | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 11.5 | O'Brian, Jamie | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mosley,Joshua | Surveyor
THOMPSON,Cheryl | HSET
SKINNER,Jamie | Supervisor |  |  |  |  | Midwest Kerbing
TONER, Ultan | Supervisor | 12 |  |  |  | Daly,Troy | Specialist | 10
[6 empty] | x3 labourers | Specialist | 30
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 |  |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 4 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 3 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153
5t Excavator | A118 | 5
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256
Positrak SSL | SSL08 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Area awareness
Hazards Reported: | Nil
Incident Free Days | 20
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07B implemented (Closure Notification Upcoming)
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
.Paving removal @ foreshore |  |  | Kerbers on site contd works on FK
.Import of red gravel for shut down topup |  |  | Comms/CCTV/Irrigation Exposed for trench shut works
.Bedding below gas line @ foreshore completed
Photos

## 106
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-13
Project Location: | Geraldton | [5 empty] | Day: | Saturday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 106 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 41km/h NW Precip: 2.6 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | Khegan Brockman | Labourer
GRIFFITHS, Daniel | Project Manager | 10 | Hanly,Thomas | Operator |  | Daniel McAuffile | Operator
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 9 | O'Brian, Jamie | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mosley,Joshua | Surveyor
THOMPSON,Cheryl | HSET
SKINNER,Jamie | Supervisor |  |  |  |  | Midwest Kerbing
TONER, Ultan | Supervisor | 9 |  |  |  | Daly,Troy | Specialist
[6 empty] | x3 labourers | Specialist
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 |  |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 6 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03
Multi Roller | 256
Positrak SSL | SSL08
Grader | SLS01
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Area awareness
Hazards Reported: | Nil
Incident Free Days | 19
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07B implemented (Closure Notification Upcoming)
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Additional Service Investigation Eastern Side of Foreshore Drive
Photos

## 107
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-15
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 107 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 19 degrees Wind: 52km/h SW Precip: 3.6 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Khegan Brockman | Labourer | 0
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator |  | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 13 | O'Brian, Jamie | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mosley,Joshua | Surveyor | 12
THOMPSON,Cheryl | HSET |  |  |  |  | Mullin, Connell | Operator | 12
SKINNER,Jamie | Supervisor | 13
TONER, Ultan | Supervisor | 13 |  |  |  | Midwest Kerbing
[6 empty] | Daly,Troy | Specialist | 5
[6 empty] | x3 labourers | Specialist | 15
Herrings Gas
[6 empty] | Herring, Chris | Gas Fitter | 5
[6 empty] | x2 fitters | Gas Fitter | 10
Mid Coast Civil
[6 empty] | Vermeer, Paul | Labourer | 10
[6 empty] | Patroni, Rodney | Labourer | 10
Superstruct
[6 empty] | Ferstat, Blair | Labourer | 10
[6 empty] | x3 labourers | Labourer | 30
Oaks Civil
[6 empty] | Traffic Controllers x5 | Traffic Controller
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 6 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 5 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 8 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 6 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 8
5t Excavator | A118 | 5
Padfoot/ Smooth Drum Roller | RR 03 | 4
Multi Roller | 256
Positrak SSL | SSL08 | 7
6 Wheel Tipper | T091 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal Noted Additional Material needed to be removed beneath the pavers
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Shut Down Area, Positive Comms and Keep Clear of Machinery
Hazards Reported: | Nil
Incident Free Days | 20
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07A implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Commenced Demolition Works in Foreshore Drive Shut Down
Trenched and Backfilled, Water, Gas, Irrigation and CCTV in Foreshore Drive Shut Down
Formed and inspected Northern and Western Ramp in Foreshore Drive Shut Down
Photos

## 108
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-16
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 108 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 20 degrees Wind: 33km/h SSW Precip: 0.4 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Khegan Brockman | Labourer | 0
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator |  | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer | 12 | McGahon,Aideen | Operator | 12 | O'Brian, Jamie | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mosley,Joshua | Surveyor | 11
THOMPSON,Cheryl | HSET |  |  |  |  | Mullin, Connell | Operator | 12
SKINNER,Jamie | Supervisor | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Herrings Gas
[6 empty] | Herring, Chris | Gas Fitter | 5
[6 empty] | 1x Labourer | Gas Fitter | 5
Mid Coast Civil
[6 empty] | Vermeer, Paul | Labourer | 10
[6 empty] | Patroni, Rodney | Labourer | 10
Superstruct
[6 empty] | Ferstat, Blair | Labourer | 10
[6 empty] | x3 Labourers | Labourer | 30
Oaks Civil
[6 empty] | Traffic Controllers x5 | Traffic Controller
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 6 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 5 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 8 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 6 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 8
5t Excavator | A118 | 5
Padfoot/ Smooth Drum Roller | RR 03 | 3
Multi Roller | 256 | 3
Positrak SSL | SSL08 | 5
6 Wheel Tipper | T091 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
1 | Scheduled Service |  | Smooth Drum Roller
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal Noted Additional Material needed to be removed beneath the pavers Confirmed alignment shift of south eastern tie in to flush kerb alignment
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Shut Down Area, Positive Comms and Keep Clear of Machinery
Hazards Reported: | Nil
Incident Free Days | 21
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07A implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Demolition Works in Foreshore Drive Shut Down
Basecourse Top up and Roll
Commenced Trimming of basecourse
Pressure Testing Compelted
Connected Irrigation Mainline
Poured Northern and Western Ramp, Formed and Poured Southern Ramp
Photos

## 109
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-17
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 109 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 21 degrees Wind: 39km/h SSW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager | 12 | Asmatullayev, Ikhtiyar | Labourer | 12 | Khegan Brockman | Labourer | 0
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | O'Brian, Jamie | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mosley,Joshua | Surveyor | 11
THOMPSON,Cheryl | HSET |  |  |  |  | Mullin, Connell | Operator | 12
SKINNER,Jamie | Supervisor | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Mid Coast Civil
[6 empty] | Vermeer, Paul | Labourer | 10
[6 empty] | Patroni, Rodney | Labourer | 10
Superstruct
[6 empty] | Ferstat, Blair | Labourer | 3
[6 empty] | x3 Labourers | Labourer | 9
Oaks Civil
[6 empty] | Traffic Controllers x5 | Traffic Controller
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 5 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 6 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 7 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 8
5t Excavator | A118 | 8
Padfoot/ Smooth Drum Roller | RR 03
Multi Roller | 256 | 3
Positrak SSL | SSL08 | 8
6 Wheel Tipper | T091 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
1 | Scheduled Service |  | Smooth Drum Roller
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal Noted Additional Material needed to be removed beneath the pavers Confirmed alignment shift of south eastern tie in to flush kerb alignment
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Shut Down Area, Positive Comms and Keep Clear of Machinery
Hazards Reported: | Nil
Incident Free Days | 22
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07A implemented
Progress Meeting
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Basecourse Top up and Roll
Ongoing Trimming of basecourse
Removal of top of of Pits to allow for trimming nearby
Stripping of Formwork
Photos

## 110
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-18
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 110 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 21 degrees Wind: 39km/h SSW Precip: 0.6 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Khegan Brockman | Labourer | 0
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator |  | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | O'Brian, Jamie | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mosley,Joshua | Surveyor | 11
THOMPSON,Cheryl | HSET |  |  |  |  | Mullin, Connell | Operator | 12
SKINNER,Jamie | Supervisor | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Mid Coast Civil
[6 empty] | Vermeer, Paul | Labourer | 10
[6 empty] | Patroni, Rodney | Labourer | 10
Oaks Civil
[6 empty] | Traffic Controllers x5 | Traffic Controller
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 6 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 5 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 8 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 6 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 8
5t Excavator | A118 | 5
Padfoot/ Smooth Drum Roller | RR 03 | 3
Multi Roller | 256 | 3
Positrak SSL | SSL08 | 5
6 Wheel Tipper | T091 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
1 | Scheduled Service |  | Smooth Drum Roller
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal Noted Additional Material needed to be removed beneath the pavers Confirmed alignment shift of south eastern tie in to flush kerb alignment Flush Kerb Alignment near paving enterence amended to avoid clash with drainage pit
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Shut Down Area, Positive Comms and Keep Clear of Machinery
Hazards Reported: | Nil
Incident Free Days | 23
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07A implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing Basecourse Top up and Roll
Ongoing Trimming of basecourse
Raising of Pits in Shutdown Area
Trimming of batters and verges
Commence Reinstatement of Verges to Museum Place
Photos

## 111
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-19
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 111 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 22 degrees Wind: 41km/h SSW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Khegan Brockman | Labourer | 0
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | Daniel McAuffile | Operator | 10
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | O'Brian, Jamie | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mosley,Joshua | Surveyor | 7
THOMPSON,Cheryl | HSET |  |  |  |  | Mullin, Connell | Operator | 12
SKINNER,Jamie | Supervisor | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Mid Coast Civil
[6 empty] | Vermeer, Paul | Labourer | 10
[6 empty] | Patroni, Rodney | Labourer | 10
Midwest Kerbing
[6 empty] | Daly,Troy | Specialist | 8
[6 empty] | x3 labourers | Specialist | 24
Oaks Civil
[6 empty] | Traffic Controllers x5 | Traffic Controller
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site:
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 3 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 5 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 5 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 10
5t Excavator | A118 | 2
Padfoot/ Smooth Drum Roller | RR 03 | 2
Multi Roller | 256 | 3
Positrak SSL | SSL08 | 5
6 Wheel Tipper | T091 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
1 | Scheduled Service |  | Smooth Drum Roller
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal Noted Additional Material needed to be removed beneath the pavers Confirmed alignment shift of south eastern tie in to flush kerb alignment
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Shut Down Area, Positive Comms and Keep Clear of Machinery
Hazards Reported: | Nil
Incident Free Days | 24
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07A implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Trimming of basecourse areas around the pit and final survey checks
Tidy up of paving tie ins
Greasing of Lids
Trimming of batters and verges
Photos

## 112
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-20
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 112 | [5 empty] | Finish: | 18:00
WEATHER & GROUND CONDITIONS
Temperature: 25 degrees Wind: 39km/h SSE Precip: 0.2 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Khegan Brockman | Labourer | 0
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | Daniel McAuffile | Operator | 0
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | O'Brian, Jamie | Operator | 0
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mosley,Joshua | Surveyor | 2
THOMPSON,Cheryl | HSET |  |  |  |  | Mullin, Connell | Operator | 12
SKINNER,Jamie | Supervisor
TONER, Ultan | Supervisor | 12 |  |  |  | Pavers (ACP)
[6 empty] | Yelland, Tony | Paving Foreman | 10
[6 empty] | Pavers x 5 | Pavers | 50
Oaks Civil
[6 empty] | Traffic Controllers x5 | Traffic Controller
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 3 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 5 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 5 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 7
5t Excavator | A118 | 2
Padfoot/ Smooth Drum Roller | RR 03 | 2
Multi Roller | 256 | 3
Positrak SSL | SSL08 | 5
6 Wheel Tipper | T091 | 5
Grader | SLS01
0 | Repairs Required |  | N/A
1 | Scheduled Service |  | Smooth Drum Roller
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal Noted Additional Material needed to be removed beneath the pavers Confirmed alignment shift of south eastern tie in to flush kerb alignment
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Shut Down Area, Positive Comms and Keep Clear of Machinery
Hazards Reported: | Nil
Incident Free Days | 25
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07A implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Commencement of Paving Installation
Trimming of batters and verges
Photos

## 113
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-21
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 113 | [5 empty] | Finish: | 17:00
WEATHER & GROUND CONDITIONS
Temperature: 30 degrees Wind: 44km/h E Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 11 | Khegan Brockman | Labourer | 0
GRIFFITHS, Daniel | Project Manager | 10 | Hanly,Thomas | Operator | 11 | Daniel McAuffile | Operator | 0
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 11 | O'Brian, Jamie | Operator | 0
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mosley,Joshua | Surveyor | 0
THOMPSON,Cheryl | HSET |  |  |  |  | Mullin, Connell | Operator | 11
SKINNER,Jamie | Supervisor
TONER, Ultan | Supervisor | 11 |  |  |  | Pavers (ACP)
[6 empty] | Yelland, Tony | Paving Foreman | 8
[6 empty] | Pavers x 5 | Pavers | 40
Oaks Civil
[6 empty] | Traffic Controllers x5 | Traffic Controller | 37.5
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 3 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 5 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 5 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 7
5t Excavator | A118 | 2
Padfoot/ Smooth Drum Roller | RR 03
Multi Roller | 256
Positrak SSL | SSL08 | 5
6 Wheel Tipper | T091
Grader | SLS01
0 | Repairs Required |  | N/A
1 | Scheduled Service |  | Smooth Drum Roller
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Kerbing Plan reissued by TCD Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage and Light Pole Removal Noted Additional Material needed to be removed beneath the pavers Confirmed alignment shift of south eastern tie in to flush kerb alignment
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Shut Down Area, Positive Comms and Keep Clear of Machinery
Hazards Reported: | Nil
Incident Free Days | 0
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 1 | Excavator Bucket made contact with Loader Light
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
TGS MB1119-07A implemented
Road Opened at Approx 1530 Aftercare Signage Installed
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Completion of Paving Install
Boxing out of Limestone Block Pits
Temp Reinstatement of Verges in Shutdown Area Reinstallation of original site fencing
Trimming of batters and verges
Photos

## 114
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-22
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 114 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 30 degrees Wind: 52km/h ENE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Daniel McAuffile | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | O'Brian, Jamie | Operator | 0
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 4
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mullin, Connell | Operator | 12
THOMPSON,Cheryl | HSET | 12
SKINNER,Jamie | Supervisor
TONER, Ultan | Supervisor | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 5 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 2 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 8
5t Excavator | A118 | 2
Padfoot/ Smooth Drum Roller | RR 03
Multi Roller | 256
Positrak SSL | SSL08 | 5
6 Wheel Tipper | T091 | 5
Grader | SLS01 | 8
0 | Repairs Required |  | N/A
1 | Scheduled Service |  | Smooth Drum Roller
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Good Effort on Shutdown
Hazards Reported: | Nil
Incident Free Days | 1
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Cement Stabilisation of Electrical Cable
Subgrade Prep Monument Parade to Bayley
Import Landscaping Soil
Trimming of batters
Boxout of Limestone Blocks
Photos

## 115
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-23
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 115 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 30 degrees Wind: 43km/h NE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Daniel McAuffile | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | O'Brian, Jamie | Operator | 10
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 6
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mullin, Connell | Operator | 12
THOMPSON,Cheryl | HSET | 12
SKINNER,Jamie | Supervisor |  |  |  |  | Geraldton Natural Limestone | Labourers | 40
TONER, Ultan | Supervisor | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 5 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 2 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 8
5t Excavator | A118 | 2
Padfoot/ Smooth Drum Roller | RR 03
Multi Roller | 256
Positrak SSL | SSL08 | 5
6 Wheel Tipper | T091 | 5
Grader | SLS01 | 8
0 | Repairs Required |  | N/A
1 | Scheduled Service |  | Smooth Drum Roller Completed Today
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 2
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Subgrade Prep Monument Parade to Bayley inc Proof Roll and Testing
Limestone Blockwork
Sump Works
Boxout of Limestone Blocks
Photos

## 116
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-24
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 116 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 32 degrees Wind: 35km/h NE Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Daniel McAuffile | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | O'Brian, Jamie | Operator | 10
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 5
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Mullin, Connell | Operator | 12
THOMPSON,Cheryl | HSET
SKINNER,Jamie | Supervisor |  |  |  |  | Geraldton Natural Limestone | Labourers | 40
TONER, Ultan | Supervisor | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 5 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 2 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 10
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03 | 6
Multi Roller | 256
Positrak SSL | SSL08 | 5
6 Wheel Tipper | T091 | 3
Grader | SLS01 | 9
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Truck Movements
Hazards Reported: | Nil
Incident Free Days | 3
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Subgrade Prep Monument Parade to Bayley inc Proof Roll and Testing
Trimming of batters/ Footpath area
Boxout of Limestone Blocks
Limestone Block Install
Photos

## 117
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-25
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 117 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 30 degrees Wind: 30km/h S Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Daniel McAuffile | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | Mosley,Joshua | Surveyor | 6
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Mullin, Connell | Operator | 12
GRIFFITHS, Ashley | Supervisor
THOMPSON,Cheryl | HSET |  |  |  |  | Geraldton Natural Limestone | Labourers | 40
SKINNER,Jamie | Supervisor
TONER, Ultan | Supervisor | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 5 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 2 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 8
5t Excavator | A118 | 2
Padfoot/ Smooth Drum Roller | RR 03
Multi Roller | 256
Positrak SSL | SSL08 | 5
6 Wheel Tipper | T091 | 5
Grader | SLS01 | 8
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 4
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Subbase Import Monument Parade to Bayley
Trimming of batters/ Footpath area
Limestone Block Install
Boxout of Limestone Blocks
Photos

## 118
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-26
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 118 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 26 degrees Wind: 43km/h SSW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | Daniel McAuffile | Operator | 10
GRIFFITHS, Daniel | Project Manager | 8 | Hanly,Thomas | Operator | 12 | Mosley,Joshua | Surveyor
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Mullin, Connell | Operator | 12
GRIFFITHS, Ashley | Supervisor
THOMPSON,Cheryl | HSET |  |  |  |  | Geraldton Natural Limestone | Labourers | 40
SKINNER,Jamie | Supervisor
TONER, Ultan | Supervisor | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 5 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 2 |  |  |  | Temp Fence |  | 1
14t Excavator with GPS | EX153 | 8
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256
Positrak SSL | SSL08 | 5
Grader | SLS01 | 9
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | Make site safe for the long weekend
Hazards Reported: | Nil
Incident Free Days | 0
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | Incident
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Basecourse Import & Sub-base Proof Roll to Bayley Street End
Trimming of batters/ Footpath area
Limestone Block Install
Removal of Laterals and commence trenching to Chambers way in anticipatation of new gas alignment
Photos

## 119
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-09-30
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 119 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 43km/h SW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | McAuffile, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator |  | Mosley,Joshua | Surveyor | 6
O"SHEA, John | Senior Project Engineer | 12 | McGahon,Aideen | Operator | 12 | Mullin, Connell | Operator | 12
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Keady, Brendan | Operator | 12
THOMPSON,Cheryl | HSET |  |  |  |  | Griffiths, Jaquai | Operator | 10
SKINNER,Jamie | Supervisor |  |  |  |  | Geraldton Natural Limestone | Labourers | 20
TONER, Ultan | Supervisor | 12 |  |  |  | Superstruct | Concreters | 40
[6 empty] | Ivac | Vac Truck | 20
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 5 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 2 |  |  |  | Temp Fence |  | 1
8T Wheeled Excavator | BCC12
14t Excavator with GPS | EX153 | 8
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03 | 5
Multi Roller | 256 | 2
Positrak SSL | SSL08 | 5
Grader | SLS01 | 9
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Direction on Service Clash Forrest Street Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Underground Services
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 1
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Basecourse Placement
Trimming of batters/ Footpath area
Limestone Block Install
Commenced Vacuum Excavating Corner of Chambers and Monument
Commenced Concrete Ramp Installs
Photos