## 120
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-01
Project Location: | Geraldton | [5 empty] | Day: | Wednesday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 120 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 25 degrees Wind: 44km/h S Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | McAuffile, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator |  | Mosley,Joshua | Surveyor | 6
O"SHEA, John | Senior Project Engineer | 12 | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Geraldton Natural Limestone | Labourers | 20
SKINNER,Jamie | Supervisor |  |  |  |  | Superstruct | Concreters | 40
TONER, Ultan | Supervisor | 12 |  |  |  | Ivac | Vac Truck | 20
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 5 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 | 8 |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 1 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 2 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12
14t Excavator with GPS | EX153 | 9
Roller (1.5t) | R538
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03 | 7
Multi Roller | 256 | 4
Positrak SSL | SSL08 | 8
Grader | SLS01 | 10.5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 2
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Final Trim Basecourse NDM Testing and Drybacks
Placed Water Pipework
Ongoing Vacuum Excavating Corner of Chambers and Monument
Form and Pour Concrete Ramps
Photos

## 121
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-02
Project Location: | Geraldton | [5 empty] | Day: | Thursday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 121 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 32 degrees Wind: 30km/h SW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator |  | Mosley,Joshua | Surveyor | 6
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Geraldton Natural Limestone | Labourers | 20
SKINNER,Jamie | Supervisor |  |  |  |  | Superstruct | Concreters | 33
TONER, Ultan | Supervisor | 12 |  |  |  | Ivac | Vac Truck | 20
[6 empty] | Catwest Sealing Crew | Sealing Crew | 10
[6 empty] | Herrings Plumbing (Gas Installers) | Gas Installer | 20
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 3 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 | 5 |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 1 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 2 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12
14t Excavator with GPS | EX153 | 8
Roller (1.5t) | R538 | 5
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03 | 3
Multi Roller | 256 | 8
Positrak SSL | SSL08 | 8
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25)
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 3
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Primer Seal
Installed Gas-Pipework (Line Pressurised)
Water Adjustments in line with GH Comments at Forrest Street End
Excavation for Garden Bed Kerbing
Ongoing Vacuum Excavating Corner of Chambers and Commenced Vac Trucking Foreshore Drive
Adjusted Irrigation Mainline to Suit New Services Alignment
Form and Pour Concrete Ramps
Photos

## 122
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-03
Project Location: | Geraldton | [5 empty] | Day: | Friday
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 122 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 44km/h W Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator |  | Mosley,Joshua | Surveyor | 2
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Vermeer, Paul | Labourer | 11
SKINNER,Jamie | Supervisor |  |  |  |  | Superstruct | Concreters | 33
TONER, Ultan | Supervisor | 12 |  |  |  | Ivac | Vac Truck | 20
[6 empty] | Herrings Plumbing (Gas Installers) | Gas Installer | 5
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 3 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 6 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 5
14t Excavator with GPS | EX153 | 3
Roller (1.5t) | R538 | 2
5t Excavator | A118
Padfoot/ Smooth Drum Roller | RR 03 | 3
Multi Roller | 256 | 2
Positrak SSL | SSL08 | 8
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage Verbal Instruction Given to End Cap Water at Forrest Street End ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25)
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 4
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Lid Setting Bayley Street End
ATCO Gas Confirmed that Pressure Test is Conforming
Pressure Testng of Waterpipe (Held) Witnessed by GH and Steve Barac
Excavation for Planter Kerbing
Miscellanous Vac Truck works and Demob
Form and Pour Concrete Ramps
Photos

## 123
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-04
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 123 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 25 degrees Wind:50km/h NW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 10 | Hanly,Thomas | Operator |  | Mosley,Joshua | Surveyor
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator
THOMPSON,Cheryl | HSET |  |  |  |  | Vermeer, Paul | Labourer
SKINNER,Jamie | Supervisor
TONER, Ultan | Supervisor | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 6 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 3 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 1 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12
14t Excavator with GPS | EX153 | 3
Roller (1.5t) | R538 | 5
5t Excavator | A118 | 5
Positrak SSL | SSL08 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage Verbal Instruction Given to End Cap Water at Forrest Street End ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25)
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 5
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Build up Verge post Kerbing
Exposing Retic Laterals for Future Connection
Photos

## 124
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-06
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 124 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 52km/h SSW Precip: 2.4 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager |  | Hanly,Thomas | Operator |  | Mosley,Joshua | Surveyor | 2
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Vermeer, Paul | Labourer | 11
SKINNER,Jamie | Supervisor | 12 |  |  |  | Goodwin, Noah | Labourer | 10
TONER, Ultan | Supervisor | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 6 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 5 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 4 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 4
14t Excavator with GPS | EX153 | 3
Roller (1.5t) | R538 | 4
5t Excavator | A118
Positrak SSL | SSL08 | 5
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage Verbal Instruction Given to End Cap Water at Forrest Street End ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25)
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 6
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Setting Lids Bayley Street End
Build up Verge post Kerbing
Setting of NBN Pits
Strip Formwork to Wombat Ramps
Trenching of Kerbing
Photos

## 125
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-07
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 125 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 46km/h SSW Precip: 0.2 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager |  | Hanly,Thomas | Operator | 12 | Mosley,Joshua | Surveyor | 2
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Vermeer, Paul | Labourer | 11
SKINNER,Jamie | Supervisor | 12 |  |  |  | Goodwin, Noah | Labourer | 10
TONER, Ultan | Supervisor | 12 |  |  |  | Kerbers | Labourer | 30
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 2 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 5 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 8 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 4
14t Excavator with GPS | EX153
Roller (1.5t) | R538 | 2
Positrak SSL | SSL08 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage Verbal Instruction Given to End Cap Water at Forrest Street End ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25)
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 7
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Setting Lids Bayley Street End
Build up Verge post Kerbing
Kerbing Works
Setting Pits
Trenching of Garden Beds
Photos

## 126
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-08
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 126 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 46km/h SSW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager |  | Hanly,Thomas | Operator | 12 | Mosley,Joshua | Surveyor | 2
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Vermeer, Paul | Labourer | 11
SKINNER,Jamie | Supervisor | 12 |  |  |  | Goodwin, Noah | Labourer | 10
TONER, Ultan | Supervisor | 12 |  |  |  | Kerbers | Labourer | 30
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 4 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 3 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 7 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 7
14t Excavator with GPS | EX153
Roller (1.5t) | R538 | 1
Positrak SSL | SSL08 | 4
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage Verbal Instruction Given to End Cap Water at Forrest Street End ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25)
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 8
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Build up Verge post Kerbing
Kerbing Works
Lid Setting
Setting Pits
Install of Light Poles
Photos

## 127
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-09
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 127 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 44km/h S Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager |  | Hanly,Thomas | Operator | 12 | Mosley,Joshua | Surveyor | 4
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Goodwin, Noah | Labourer | 10
SKINNER,Jamie | Supervisor | 12 |  |  |  | Kerbers | Labourer | 30
TONER, Ultan | Supervisor | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 2 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 6 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 6 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 5
14t Excavator with GPS | EX153 | 10
Roller (1.5t) | R538
Positrak SSL | SSL08 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage Verbal Instruction Given to End Cap Water at Forrest Street End ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25)
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 9
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Build up Verge post Kerbing
Kerbing Works
Pit Setting (NBN and Power)
Excavate and Set Bollards
Install of Light Poles
Photos

## 128
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-10
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 128 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 46km/h SW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager |  | Hanly,Thomas | Operator | 12 | Mosley,Joshua | Surveyor
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Goodwin, Noah | Labourer | 10
SKINNER,Jamie | Supervisor | 12 |  |  |  | Vac Truck | Operators | 18
TONER, Ultan | Supervisor | 12 |  |  |  | Kerbers | Labourer | 30
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 2 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 6 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 6 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 5
14t Excavator with GPS | EX153 | 10
Roller (1.5t) | R538
Positrak SSL | SSL08 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage Verbal Instruction Given to End Cap Water at Forrest Street End ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25)
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | PPE
Hazards Reported: | Nil
Incident Free Days | 10
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Build up Verge post Kerbing
Kerbing Works
Pit Setting (NBN and Power)
Exposure of Laterals in Tree Pits
Trenching of Garden Bed Kerb
Tidy of Verges
Photos

## 129
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-11
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 129 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 46km/h SW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager |  | Hanly,Thomas | Operator | 12 | Mosley,Joshua | Surveyor
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator
THOMPSON,Cheryl | HSET |  |  |  |  | Goodwin, Noah | Labourer
SKINNER,Jamie | Supervisor |  |  |  |  | Vac Truck | Operators
TONER, Ultan | Supervisor | 12 |  |  |  | Kerbers | Labourer
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 6 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 5 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 6 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 6 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12
14t Excavator with GPS | EX153
Roller (1.5t) | R538
Positrak SSL | SSL08 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
New Detail Provided on Centrelink Carpark Awaiting Confirmation on Batters Treatment Awaiting finalised fencing details Awaiting COGG confirmation on "Ballast Pile" Instructions Provided for Laneway Sewer, Drainage Verbal Instruction Given to End Cap Water at Forrest Street End ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25)
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | PPE
Hazards Reported: | Nil
Incident Free Days | 11
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Build up Verge post Kerbing
Kerbing Works
Pit Setting (NBN and Power)
Exposure of Laterals in Tree Pits
Trenching of Garden Bed Kerb
Tidy of Verges
Photos

## 130
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-13
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 130 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 46km/h SW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 10 | Hanly,Thomas | Operator | 12 | Mosley,Joshua | Surveyor | 2
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Goodwin, Noah | Labourer | 10
SKINNER,Jamie | Supervisor | 12 |  |  |  | Vac Truck | Operators
TONER, Ultan | Supervisor | 12 |  |  |  | Kerbers | Labourer | 40
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 5 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 | 4 |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 2 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 6 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 4
14t Excavator with GPS | EX153 | 4
Roller (1.5t) | R538 | 1
Positrak SSL | SSL08 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Verbal Instruction Given to End Cap Water at Forrest Street End ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25)
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 12
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Verge Trimming for Pavers
Garden Bed Kerbing Works
Pit Setting (NBN and Power)
Exposure of Laterals in Tree Pits
ACP Mobilised ot Site
Signage Installs
Photos

## 131
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-14
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 131 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 46km/h SW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | Mosley,Joshua | Surveyor | 5
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Goodwin, Noah | Labourer | 10
SKINNER,Jamie | Supervisor | 12 |  |  |  | Vac Truck | Operators | 20
TONER, Ultan | Supervisor | 12 |  |  |  | Kerbers | Labourer | 40
[6 empty] | Pavers | Labourers | 50
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 5 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 | 4 |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 2 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 6 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 4
14t Excavator with GPS | EX153 | 4
Roller (1.5t) | R538 | 1
Positrak SSL | SSL08 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25) Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services. Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction. Changes occured after light poles were excavated.
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 12
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Verge Trimming for Pavers
Garden Bed Kerbing Works
Pit Setting (NBN and Power)
Light pole excavation
Exposure of Laterals in Tree Pits
Commencement of Paving
Signage Installs
Photos

## 132
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-15
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 132 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 41km/h S Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | Mosley,Joshua | Surveyor | 4
O"SHEA, John | Senior Project Engineer | 12 | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Goodwin, Noah | Labourer | 10
SKINNER,Jamie | Supervisor | 12 |  |  |  | Vac Truck | Operators | 20
TONER, Ultan | Supervisor | 12 |  |  |  | Kerbers | Labourer | 40
[6 empty] | Pavers | Labourers | 50
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 | 5 |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 4 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 7 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 4
14t Excavator with GPS | EX153 | 9
Roller (1.5t) | R538 | 0
Positrak SSL | SSL08 | 0
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25) Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were excavated.
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 14
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Verge Trimming for Pavers
Garden Bed Kerbing Works
Pit Setting (NBN and Power)
Light pole excavation
Exposure of Laterals in Tree Pits
Ongoing paving TO Eastern Side of Project
Photos

## 133
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-16
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 133 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 28 degrees Wind: 43km/h SSW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | Mosley,Joshua | Surveyor | 4
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Kerbers | Labourer | 40
SKINNER,Jamie | Supervisor | 12 |  |  |  | Pavers | Labourers | 50
TONER, Ultan | Supervisor | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 1 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 3 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 | 8 |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 2 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 9 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 6
14t Excavator with GPS | EX153 | 10
Roller (1.5t) | R538 | 5
Positrak SSL | SSL08 | 1
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25) Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were excavated.
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 15
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Verge Trimming for Pavers
Tree Pit Preparation
Form of Pram Ramps and On Ramps Forrest Street
Light Pole Installation
Ongoing paving
Photos

## 134
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-17
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 134 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 34 degrees Wind: 43km/h W Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | Hanly,Thomas | Operator | 12 | Mosley,Joshua | Surveyor
O"SHEA, John | Senior Project Engineer |  | McGahon,Aideen | Operator | 12 | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Vac Truck | Operators | 20
SKINNER,Jamie | Supervisor | 12 |  |  |  | Kerbers | Labourer | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Pavers | Labourers | 50
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 1 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 | 6 |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 2 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 8 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 2
14t Excavator with GPS | EX153 | 8
Roller (1.5t) | R538 | 0
Positrak SSL | SSL08 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25) Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were excavated.
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 16
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Verge Trimming for Pavers
Tree Pit Preparation
Form of Pram Ramps and On Ramps Forrest Street
Kerbers Stopped Early Unable to Obtain Concrete
Setting of Lids
Ongoing paving
Photos

## 135
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-18
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 135 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 25 degrees Wind: 43km/h W Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor
O"SHEA, John | Senior Project Engineer |  |  |  |  | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator
THOMPSON,Cheryl | HSET |  |  |  |  | Goodwin, Noah | Labourer
SKINNER,Jamie | Supervisor |  |  |  |  | Pavers | Labourers | 25
TONER, Ultan | Supervisor | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours: |  |  | 316.16 | 718.79 | 208.65 | 54.35 | 15.84
Total Direct Personnel hours: | [12 empty] | 51
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty | 473.03
Komatsu WA320 | FWL18 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1 | 125
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1 | 230
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2 | 21
8T Excavator | AMG 014 | 2 |  |  |  | Skip Bin |  | 1 | 38.92
Mini Tipper | SLS05 | 2 |  |  |  | Hydrocarbon Bund |  | 1 | 48
1 t Excavator | SLS03 | 6 |  |  |  | Temp Fence |  | 1 | 64
8T Excavator (Wheeled) | BCC12 | 4 | [6 empty] | 52
14t Excavator with GPS | EX153
Roller (1.5t) | R538
Positrak SSL | SSL08
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25) Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were excavated.
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Manual Handling
Hazards Reported: | Nil
Incident Free Days | 17
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Verge Trimming for Pavers
Prepping of Damaged Seal for Asphalt
Paving Stopped Due to Rain
Photos

## 136
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-20
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 136 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 57km/h S Precip: 1 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 8
O"SHEA, John | Senior Project Engineer |  |  |  |  | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Kerbers | Labourers | 25
SKINNER,Jamie | Supervisor | 12 |  |  |  | Asphalters | Asphalters | 120
TONER, Ultan | Supervisor | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 0 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 | 6 |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 3 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 8 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 3
14t Excavator with GPS | EX153 | 8
Roller (1.5t) | R538 | 1
Positrak SSL | SSL08 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25) Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were excavated.
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 18
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Patching of Seal
Setting of Pits
Commenced Asphalt Works
Adjustment of Pit Levels
Tree Pit Excavation
Trimming of Verges for Pavers
Photos

## 137
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-21
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 137 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 46km/h SSW Precip: 1.4 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 8
O"SHEA, John | Senior Project Engineer | 12 |  |  |  | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | McConnell, Adam | Labourer | 12
THOMPSON,Cheryl | HSET |  |  |  |  | Griffiths, Jaquai | Operator | 10
SKINNER,Jamie | Supervisor | 12 |  |  |  | Asphalters | Asphalters | 120
TONER, Ultan | Supervisor | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 | 7 |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 3 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 6 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 2
14t Excavator with GPS | EX153 | 8
Roller (1.5t) | R538 | 1
Positrak SSL | SSL08 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25) Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were excavated.
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 19
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Patching of Seal
Setting of Pits & Redirecting Conflicting Irrigation Laterals
Asphalting Monument South
Trimming of Verges for Pavers
Photos

## 138
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-22
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 138 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 25 degrees Wind: 44km/h S Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 8
O"SHEA, John | Senior Project Engineer |  |  |  |  | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Asphalters | Asphalters | 120
SKINNER,Jamie | Supervisor | 12 |  |  |  | Ferstat, Frank | Operator | 8.5
TONER, Ultan | Supervisor | 12 |  |  |  | McConnell, Adam | Labourer | 12
JOGI, Amit | Project Engineer | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 2 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 3 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 | 4 |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 2 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 8 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 4
14t Excavator with GPS | EX153 | 8
Roller (1.5t) | R538 | 3
Positrak SSL | SSL08 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25) Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were vacuum excavated.
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 20
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Patching of Seal
Setting of Pits & Redirecting Conflicting Irrigation Laterals
Exposure of Gas Pipe Bayley Street
Ongoing Asphalt Works
Trimming of Verges for Pavers
Photos

## 139
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-23
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 139 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 24 degrees Wind: 44km/h SW Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 8
O"SHEA, John | Senior Project Engineer | 12 |  |  |  | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | Asphalters | Asphalters | 120
SKINNER,Jamie | Supervisor | 6 |  |  |  | Vac Truck | Labourers | 16
TONER, Ultan | Supervisor | 12 |  |  |  | Elite Electrical | Electricians | 15
JOGI, Amit | Project Engineer | 12 |  |  |  | Traffic Controllers | Labourers | 8
[6 empty] | Ferstat, Frank | Operator | 4.5
[6 empty] | Superstruct | Concreters | 15
[6 empty] | McConnell, Adam | Labourer | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 | 2 | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 | 8 |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 3 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 8 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 2
14t Excavator with GPS | EX153 | 9
Roller (1.5t) | R538 | 3
Positrak SSL | SSL08 | 1
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25) Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were vacuum excavated. Issues around Traffic Control have been identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 21
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Patching of Seal
Setting of Pits & Redirecting Conflicting Irrigation Laterals
Exposure of Gas Pipe Bayley Street
Relocated Light Pole Forrest Street
Pour Ramps Forrest Street End of Job
Ongoing Asphalt Works
Trimming of Verges for Pavers
Photos

## 140
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-24
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 140 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 23 degrees Wind: 46km/h WSW Precip: 0.4 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 8
O"SHEA, John | Senior Project Engineer |  |  |  |  | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator
THOMPSON,Cheryl | HSET |  |  |  |  | Asphalters | Asphalters | 120
SKINNER,Jamie | Supervisor | 6 |  |  |  | Vac Truck | Labourers | 12
TONER, Ultan | Supervisor |  |  |  |  | Ferstat, Frank | Operator | 4.5
JOGI, Amit | Project Engineer | 12 |  |  |  | Ferstat, Blair | Concretor | 2
[6 empty] | McConnell, Adam | Labourer | 12
Total Indirect Personnel onsite:
Total Indirect Personnel hours: | [5 empty] | Total Subcontractor on-site: | 13
Total Direct Personnel onsite: | [5 empty] | Total Subcontractor hours:
Total Direct Personnel hours:
PLANT & EQUIPMENT
Plant | ID | Hours | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 2 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 8 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 4
14t Excavator with GPS | EX153 | 4
Roller (1.5t) | R538 | 1
Positrak SSL | SSL08 | 2
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25) Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were vacuum excavated. Final Level of Northern Lots Determined Issues around Traffic Control have been identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 22
Other Notes
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Repaired Damaged Retic Bayley Street End to Enable Pressurisation of System
Completed Vac Trucking for Gas Connections
Punchlist Asphalt Works-COGG Inspected
Trimming of Verges
Photos

## 141
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-25
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | 140 | [5 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 23 Degrees, Wind: 41km/h SW, Precip: 0.4 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator |  | Mosley,Joshua | Surveyor
O"SHEA, John | Senior Project Engineer |  |  |  |  | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator
THOMPSON,Cheryl | HSET |  |  |  |  | Asphalters | Asphalters
SKINNER,Jamie | Supervisor |  |  |  |  | Vac Truck | Labourers
TONER, Ultan | Supervisor |  |  |  |  | Ferstat, Frank | Operator
JOGI, Amit | Project Engineer | 12 |  |  |  | Ferstat, Blair | Concretor
[6 empty] | McConnell, Adam | Labourer | 12
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC04 | 2 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 |  |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 2
14t Excavator with GPS | EX153 | 6
Roller (1.5t) | R538
Positrak SSL | SSL08
0 | Repairs Required |  | N/A
0 | Scheduled Service |  | N/A
0 |  |  | N/A
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25) Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were vacuum excavated. Final Level of Northern Lots Determined Issues around Traffic Control have been identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | SIMOPS
Hazards Reported: | Nil
Incident Free Days | 23
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
General Site Tidy
Topping up Northern Lots
Photos

## 142
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-27
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 24 0C, Wind: 57 km/h SW, Precip: 1.4 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor
O"SHEA, John | Senior Project Engineer |  |  |  |  | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
SKINNER,Jamie | Supervisor | 12 |  |  |  | Vac Truck | Labourers
TONER, Ultan | Supervisor | 12 |  |  |  | Thinkwater | Labourers | 8
JOGI, Amit | Project Engineer | 12 |  |  |  | Superstruct | Concereters | 8
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC119 | 8 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 4 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 |  |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 3
14t Excavator with GPS | EX197 | 11
Roller (1.5t) | R538 | 3
Positrak SSL | SSL08
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
ATCO Gas has advised that Piece Up has not been scheduled ETA 3 Weeks (From 2/10/25) Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were vacuum excavated. Final Level of Northern Lots Determined Issues around Traffic Control have been identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Protect Existing Works
Hazards Reported: | Nil
Incident Free Days | 24
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ground prep for pavers starting back at forest
Form disabled ramp and 4x concrete footings for furniture
Expose last 6 planters including retek pipework
Ongoing 80mm fill on lots with EX197
Further Planter Lateral Works
Verge Trimming Bayley End Bayley End
Photos

## 143
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-28
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 17-290C, Wind: 29 km/h SSW, Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 3
O"SHEA, John | Senior Project Engineer |  |  |  |  | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
SKINNER,Jamie | Supervisor | 12 |  |  |  | Vac Truck | Labourers
TONER, Ultan | Supervisor | 12 |  |  |  | Kerbers | Kerbers | 20
JOGI, Amit | Project Engineer | 12 |  |  |  | Superstruct | Concereters | 3
[6 empty] | ATCO Gas | Local Authority | 40
[6 empty] | Pavers | Pavers | 18
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC119 | 6 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS05 | 9 |  |  |  | Hydrocarbon Bund |  | 1
1 t Excavator | SLS03 | 5 |  |  |  | Temp Fence |  | 1
8T Excavator (Wheeled) | BCC12 | 3
14t Excavator with GPS | EX197 | 11
Positrak SSL | SSL08
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were vacuum excavated. Final Level of Northern Lots Determined Issues around Traffic Control have been identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Positive communications
Hazards Reported: | Nil
Incident Free Days | 25
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ground preparation for Paving
Concrete pour for Kerbs at the intersection & some sections of Chambers Street
North east with paving install ongoing
Signage install ongoing
NBN and Water Pit Setting
Excavate last of the planters and start works on root deflector
ATCO Gas Connection has been Completed
Photos

## 144
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-29
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 15-220C, Wind: 25 km/h SSW, Precip: 1.2 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 6
O"SHEA, John | Senior Project Engineer | 12 |  |  |  | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
SKINNER,Jamie | Supervisor | 12 |  |  |  | Vac Truck | Labourers
TONER, Ultan | Supervisor | 12 |  |  |  | Kerbers | Kerbers
JOGI, Amit | Project Engineer | 12 |  |  |  | Superstruct | Concereters
[6 empty] | Pavers | Pavers | 40
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | WC119 | 3 |  |  |  | Site Sentry Tower |  | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin |  | 1
Mini Tipper | SLS04 | 8.5 |  |  |  | Hydrocarbon Bund |  | 1
Skid Steer | SLS03 | 2 |  |  |  | Temp Fence |  | 1
1t Excavator | SLS02 | 8
8T Excavator (Wheeled) | BCC12 | 12
14t Excavator with GPS | EX197 | 10
Positrak SSL | SSL08
IT Loader | LD011 | 10
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were vacuum excavated. Final Level of Northern Lots Determined Issues around Traffic Control have been identified Rain Delay fapprox 2 hours- 8:30 onwards
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | PPE
Hazards Reported: | Nil
Incident Free Days | 0
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 1 | Property Damage to Watercart
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ongoing kerbing works at Country builders,Centrelink car park/forest street,Planters at chambers intersection including re work of 4metres of curved and 2metres of angled kerbing SMK-FK
North east with paving install ongoing
Ground Prep works on forest street- leveling around pits
Gound Prep works for paving at chambers street is ongoing
AMG civil continue wall around electrical mini subs
Fill & Level northern lots is ongoing
Minor Kerb Replacement to avoid trip Hazard at Chamber street ongoing
Photos

## 145
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-30
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 10-220C, Wind: 36 km/h SSE, Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer |  | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 6
O"SHEA, John | Senior Project Engineer |  |  |  |  | Keady, Brendan | Operator | 12
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
SKINNER,Jamie | Supervisor | 12 |  |  |  | Vac Truck | Labourers
TONER, Ultan | Supervisor | 12 |  |  |  | Kerbers | Kerbers | 12
JOGI, Amit | Project Engineer | 12 |  |  |  | Superstruct | Concereters
[6 empty] | Pavers | Pavers | 40
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 8 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 | 9 |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 |  |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02 | 7
8T Excavator (Wheeled) | BCC12
14t Excavator with GPS | EX197
Positrak SSL | SSL08
IT Loader | LD011 | 6
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were vacuum excavated. Final Level of Northern Lots Determined Issues around Traffic Control have been identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Push to get things done
Hazards Reported: | Nil
Incident Free Days | 1
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Asphalt Core testing Samples collected
Ground Prep Works for Paving is ongoing
Paver placement at north-east is ongoing
Capping the northern lots and tidy up
Levelled 2 pits at Forrest Street
Steve Barac Onsite from WC to discuss Water Connection
Photos

## 146
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-10-31
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 15-220C, Wind: 20 km/h WNW, Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor
O"SHEA, John | Senior Project Engineer |  |  |  |  | Keady, Brendan | Operator
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
SKINNER,Jamie | Supervisor | 12 |  |  |  | Vac Truck | Labourers
TONER, Ultan | Supervisor | 12 |  |  |  | Kerbers | Kerbers
JOGI, Amit | Project Engineer | 12 |  |  |  | Superstruct | Concereters
[6 empty] | Pavers | Pavers | 40
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 3 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 | 9 |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 | 6 |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02 | 8
8T Excavator (Wheeled) | BCC12
14t Excavator with GPS | EX197
Positrak SSL | SSL08
IT Loader | LD011 | 5
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Chambers monument lightpole impacted by relocated services Lightpole adjoining southern wombat interfacing with relocated electrical needed to be relocated closer to road. Lightpole inside garden bed relocated outside garden bed at client direction Changes occured after light poles were vacuum excavated. Final Level of Northern Lots Determined Issues around Traffic Control have been identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Prestart Checks
TCD - Daily Safety Focus: | Hydration
Hazards Reported: | Nil
Incident Free Days | 2
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Installation of Signages on Monument Promenade is ongoing
Flushing of irrigation lines is ongoing. Remaining to be completed on Monday.
Installation of Paver along NE completed and section tidy up is ongoing
Electrical pits raised to correct levels
Placement of root deflector in tree pits is ongoing
Ground Prep for paving is ongoing
Photos