## 147
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-11-01
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 16-250C, Wind: 50 km/h SSW, Precip: 0.2 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor
O"SHEA, John | Senior Project Engineer |  |  |  |  | Griffiths, Jaquai | Operator
GRIFFITHS, Ashley | Supervisor |  |  |  |  | McConnell, Adam | Labourer | 12
THOMPSON,Cheryl | HSET |  |  |  |  | Henelly, DJ | Labourer | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Pavers | Pavers | 40
JOGI, Amit | Project Engineer | 12
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 9 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 | 4 |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 |  |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02
8T Excavator (Wheeled) | BCC12
14t Excavator with GPS | EX197
Roller | R538 | 2
IT Loader | LD011 | 2
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forrest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for lightpoles in locations indicating possible service interfaces. Issues around Watercorp Connection Identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Cyclones & Wet Weather
TCD - Daily Safety Focus: | Attention to details
Hazards Reported: | Nil
Incident Free Days | 3
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ground Prep works, conditioning and rolling for Paving is ongoing
Paver placement at south-east started
Holes dug for signages using Vac Trailer
Root Deflectors placement in the tree pits
Photos

## 148
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-11-03
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 15-270C, Wind: 15 km/h SW, Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 3
O"SHEA, John | Senior Project Engineer |  |  |  |  | Levy, Laurent | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Henelly, DJ | Labourer | 12
JOGI, Amit | Project Engineer | 12 |  |  |  | Pavers | Pavers | 40
[6 empty] | Think Water | Irrigation | 8
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
Komatsu WA320 | FWL18 |  | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 4 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 | 4 |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 |  |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02
8T Excavator (Wheeled) | BCC12 | 6
14t Excavator with GPS | EX197 | 2
Roller | R538 | 2
IT Loader | LD011 | 6
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for light poles in locations indicating possible service interfaces. Issues around Watercorp Connection Identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Cyclones & Wet Weather
TCD - Daily Safety Focus: | Mind at task
Hazards Reported: | Nil
Incident Free Days | 0
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 2 | 1) LV drove into tree pit , 2) Damaged Building window
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ground Prep works, conditioning and rolling for Paving is ongoing
Commenced Haunching Eastern Side of the Project
Road marking for Foreshore Drive intersection is completed
Commissioned Irrigation Laterals
Delivery of Paver received and unloaded
Photos

## 149
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-11-04
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 16-240C, Wind: 37 km/h SW, Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 6 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 3
O"SHEA, John | Senior Project Engineer |  |  |  |  | Levy, Laurent | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Henelly, DJ | Labourer | 12
SKINNER, Jamie | Supervisor | 12 |  |  |  | Pavers | Pavers | 30
JOGI, Amit | Project Engineer | 12 |  |  |  | Think Water | Irrigation
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
IT Loader | LD011 | 6 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 5 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 | 3 |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 |  |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 | 2 |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02 | 3
1t Excavator | DEX30 | 2
8T Excavator (Wheeled) | BCC12 | 4
14t Excavator with GPS | EX197
Roller | R538 | 1
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for light poles in locations indicating possible service interfaces. Issues around Watercorp Connection Identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Cyclones & Wet Weather
TCD - Daily Safety Focus: | Vehicles and Driving Onsite
Hazards Reported: | Nil
Incident Free Days | 1
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ground Prep works, conditioning and rolling for Paving at the intersection and Chamber's way footpath are ongoing
Paving at Forrest street entrance is ongoing
Preparation for tree placement is ongoing
Electrical conduits installation in Laneway is ongoing
Photos

## 150
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-11-05
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 14-240C, Wind: 63 km/h NW, Precip: 8 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor
O"SHEA, John | Senior Project Engineer |  |  |  |  | Levy, Laurent | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Henelly, DJ | Labourer | 12
SKINNER, Jamie | Supervisor | 12 |  |  |  | Pavers | Pavers | 30
JOGI, Amit | Project Engineer | 12 |  |  |  | Think Water | Irrigation
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
IT Loader | LD011 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 2 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 | 5 |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 |  |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 |  |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02
1t Excavator | DEX30
8T Excavator (Wheeled) | BCC12 | 4
14t Excavator with GPS | EX197
Roller | R538 | 2
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for light poles in locations indicating possible service interfaces. Issues around Watercorp Connection Identified Works stopped multiple times due to rain
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Cyclones & Wet Weather
TCD - Daily Safety Focus: | Planning task
Hazards Reported: | Nil
Incident Free Days | 2
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ground Prep works, conditioning and rolling for Paving at intersection is ongoing
Paving at Forrest street entrance is ongoing
Preparation for tree placement is ongoing
Electrical conduits installation in Laneway is ongoing
Holes for furniture footings is ongoing
Photos

## 151
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-11-06
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 14-210C, Wind: 54 km/h SSW, Precip: 8 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 3
O"SHEA, John | Senior Project Engineer |  |  |  |  | Levy, Laurent | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Henelly, DJ | Labourer | 12
SKINNER, Jamie | Supervisor | 12 |  |  |  | Pavers | Pavers | 30
JOGI, Amit | Project Engineer | 12 |  |  |  | Think Water | Irrigation
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
IT Loader | LD011 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 2 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 | 7 |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 |  |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02
1t Excavator | DEX30
8T Excavator (Wheeled) | BCC12
14t Excavator with GPS | EX197 | 9
Roller | R538 | 3
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for light poles in locations indicating possible service interfaces. Issues around Watercorp Connection Identified Works stopped multiple times due to rain
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Cyclones & Wet Weather
TCD - Daily Safety Focus: | Planning task
Hazards Reported: | Nil
Incident Free Days | 3
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ground Prep works and rolling for Paving at intersection is completed
Paving at Western side heading north is ongoing
Holes dug for Furniture foootings using Vac Trailer
Electrical conduits installation in Laneway is ongoing
Ten Tigers Window Repaired
Preparation for tree placement is ongoing
Photos

## 152
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-11-07
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 13-270C, Wind: 40 km/h SW, Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 3
O"SHEA, John | Senior Project Engineer |  |  |  |  | Levy, Laurent | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Henelly, DJ | Labourer | 12
SKINNER, Jamie | Supervisor | 12 |  |  |  | Pavers | Pavers | 30
JOGI, Amit | Project Engineer | 12 |  |  |  | Think Water | Irrigation | 8
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
IT Loader | LD011 | 5 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 3 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 | 6 |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 | 2 |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02
1t Excavator | DEX30
8T Excavator (Wheeled) | BCC12
14t Excavator with GPS | EX197 | 9.5
Roller | R538 | 2.5
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for light poles in locations indicating possible service interfaces. Issues around Watercorp Connection Identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Cyclones & Wet Weather
TCD - Daily Safety Focus: | Attention to details
Hazards Reported: | Nil
Incident Free Days | 4
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ground Prep works and rolling for Paving along north west is ongoing
Paving at intersection is ongoing
Concrete poured for Furniture footings
Electrical conduits installation in Laneway is ongoing
Installation of sprinklers on irrigation line is ongoing
General Site Tidy
Preparation for Garden Beds at chambers street completed
Photos

## 153
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-11-08
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 12-320C, Wind: 52 km/h S, Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 8 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor
O"SHEA, John | Senior Project Engineer |  |  |  |  | Levy, Laurent | Operator | 10
GRIFFITHS, Ashley | Supervisor |  |  |  |  | Griffiths, Jaquai | Operator
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer
TONER, Ultan | Supervisor | 12 |  |  |  | Henelly, DJ | Labourer | 12
SKINNER, Jamie | Supervisor |  |  |  |  | Pavers | Pavers | 40
JOGI, Amit | Project Engineer | 12 |  |  |  | Think Water | Irrigation
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
IT Loader | LD011 | 1 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 4 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 | 3 |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 |  |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02
1t Excavator | DEX30 | 2
8T Excavator (Wheeled) | BCC12
14t Excavator with GPS | EX197
Roller | R538
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forest street to advise if additional adjustments required. Lateral reticulation pipes hit multiple times during NBN pit installation due to relocation within NBN alignment. Multitude of rework identified. Vacuum truck used for light poles in locations indicating possible service interfaces. Issues around Watercorp Connection Identified
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Cyclones & Wet Weather
TCD - Daily Safety Focus: | Fitness for work
Hazards Reported: | Nil
Incident Free Days | 5
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ground Prep works and rolling for Paving along north west is ongoing
Paving at intersection is completed. Paving continues on NW run.
Riverstone installation in the Garden beds is on going
General site tidy up is ongoing
Garden bed prep completed on Chambers Street
Photos

## 154
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-11-10
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 17-320C, Wind: 38 km/h SSW, Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 5
O"SHEA, John | Senior Project Engineer |  |  |  |  | Levy, Laurent | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer
TONER, Ultan | Supervisor | 12 |  |  |  | Henelly, DJ | Labourer | 12
SKINNER, Jamie | Supervisor |  |  |  |  | Pavers | Pavers | 40
JOGI, Amit | Project Engineer | 12 |  |  |  | Think Water | Irrigation
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
IT Loader | LD011 | 3 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 4 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 | 5 |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 | 7 |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 |  |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02
1t Excavator | DEX30
8T Excavator (Wheeled) | BCC12 | 5
14t Excavator with GPS | EX197
Roller | R538 | 2
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forest street to advise if additional adjustments required. Vacuum truck used for light poles in locations indicating possible service interfaces. Issues around Watercorp Connection-Connection Date now 29/11/25 impacts to Kerbing, Paving and Concrete works
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Cyclones & Wet Weather
TCD - Daily Safety Focus: | Hydration and Hot Weather
Hazards Reported: | Nil
Incident Free Days | 6
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Ground Prep works for accessable areas completed for Paving
Paving continues along North East
Haunching prep and concreting is ongoing for Western Section
Ongoing Scour Protection to Garden Beds
General site tidy up is ongoing
Formwork for Rain Garden Inlet scour protection ready for pouring 11/11/25
Placement of limestone blocks in Garden bed opposite centre link car park
Photos

## 155
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-11-11
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 18-310C, Wind: 35 km/h SSE, Precip: 1 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 5
O"SHEA, John | Senior Project Engineer |  |  |  |  | Levy, Laurent | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Henelly, DJ | Labourer | 12
SKINNER, Jamie | Supervisor |  |  |  |  | Pavers | Pavers | 40
JOGI, Amit | Project Engineer | 12 |  |  |  | Think Water | Irrigation | 10
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
IT Loader | LD011 | 2 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 6 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 | 7 |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 |  |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02 | 6
1t Excavator | DEX30
8T Excavator (Wheeled) | BCC12 | 6
14t Excavator with GPS | EX197
Roller | R538
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forest street to advise if additional adjustments required. Vacuum truck used for light poles in locations indicating possible service interfaces. Issues around Watercorp Connection-Connection Date now 29/11/25 impacts to Kerbing, Paving and Concrete works Rain delay in the afternoon
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Cyclones & Wet Weather
TCD - Daily Safety Focus: | Attention to details
Hazards Reported: | Nil
Incident Free Days | 7
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Unloading the delivery of Trees completed. Placement of trees and watering is ongoing.
Paving continues along North East
Backfilling the planters after tree placement is ongoing
Ongoing Scour Protection to Garden Beds
Rain Garden Inlet scour protection poured
Installation of Sprinklers on the irrigation Mains is ongoing
Erection of 3 light poles completed
Photos

## 156
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-11-12
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 18-330C, Wind: 35 km/h SSE, Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 5
O"SHEA, John | Senior Project Engineer | 12 |  |  |  | Levy, Laurent | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Henelly, DJ | Labourer | 12
SKINNER, Jamie | Supervisor |  |  |  |  | Pavers | Pavers | 40
JOGI, Amit | Project Engineer | 12 |  |  |  | Think Water | Irrigation | 10
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
IT Loader | LD011 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 8 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 | 3 |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 | 2 |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 | 4 |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02 | 1
1t Excavator | DEX30 | 2
8T Excavator (Wheeled) | BCC12 | 4
14t Excavator with GPS | EX197
Roller | R538
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forest street to advise if additional adjustments required. Vacuum truck used for light poles in locations indicating possible service interfaces. Issues around Watercorp Connection-Connection Date now 29/11/25 impacts to Kerbing, Paving and Concrete works, Watercorp have advised that bacteria testing and another pressure test is required
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Cyclones & Wet Weather
TCD - Daily Safety Focus: | Hydration & Cool zones
Hazards Reported: | Nil
Incident Free Days | 8
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Placement of Trees in the planters 90% completed.
Paving continues along North East
Backfilling the planters after tree placement is ongoing
Ongoing Prep for planting in Garden Beds on Saturday
Watering the plants and Terracottem backfill is ongoing
Backfill along laneway and compaction
Photos

## 157
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-11-13
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 18-330C, Wind: 35 km/h SSE, Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 5
O"SHEA, John | Senior Project Engineer | 12 |  |  |  | Levy, Laurent | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Henelly, DJ | Labourer | 12
SKINNER, Jamie | Supervisor | 12 |  |  |  | Pavers | Pavers | 40
[6 empty] | Think Water | Irrigation | 10
[6 empty] | Catwest | Asphalters
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
IT Loader | LD011 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 8 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 | 6 |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 | 2 |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02
1t Excavator | DEX30 | 2
8T Excavator (Wheeled) | BCC12 | 4
14t Excavator with GPS | EX197 | SD
Roller | R538
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forest street to advise if additional adjustments required. Issues around Watercorp Connection-Connection Date now 29/11/25 impacts to Kerbing, Paving and Concrete works, Watercorp have advised that bacteria testing and another pressure test is required Watercorp Works Request Issued
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Cyclones & Wet Weather
TCD - Daily Safety Focus: | Hydration & Cool zones
Hazards Reported: | Nil
Incident Free Days | 9
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Tree Installs Completed
Paving continues along North East
Commenceed Flushing Water Pipe in Laneway
Ongoing Prep for planting in Garden Beds on Saturday
Red Asphalt Installed
Photos

## 158
TCD DAILY FIELD REPORT
Project Name: | Batavia Station Square | [5 empty] | Date: | 2025-11-14
Project Location: | Geraldton | [5 empty] | Day:
Project Number: | TCD-1816 | [5 empty] | Start: | 6:00
Report Number: | [6 empty] | Finish: | 18:30
WEATHER & GROUND CONDITIONS
Temperature: 18-330C, Wind: 35 km/h SSE, Precip: 0 mm
PERSONNEL
TCD Indirects |  |  | TCD Directs |  |  | Subcontractors
Name | Position | Hours | Name | Position | Hours | Name | Position | Hours
WATKINS, Steve | Civil Manager |  | Asmatullayev, Ikhtiyar | Labourer | 12 | McAuliffe, Daniel | Operator | 10
GRIFFITHS, Daniel | Project Manager | 12 | McGahon,Aideen | Operator | 12 | Mosley,Joshua | Surveyor | 5
O"SHEA, John | Senior Project Engineer | 12 |  |  |  | Levy, Laurent | Operator | 10
GRIFFITHS, Ashley | Supervisor | 10 |  |  |  | Griffiths, Jaquai | Operator | 10
THOMPSON,Cheryl | HSET |  |  |  |  | McConnell, Adam | Labourer | 12
TONER, Ultan | Supervisor | 12 |  |  |  | Henelly, DJ | Labourer | 12
SKINNER, Jamie | Supervisor | 12 |  |  |  | Pavers | Pavers | 40
[6 empty] | Catwest | Asphalters
Total Indirect Personnel onsite: |  |  | Total Direct Personnel onsite: |  |  | Total Subcontractor on-site:
Total Indirect Personnel hours: |  |  | Total Direct Personnel hours: |  |  | Total Subcontractor hours:
PLANT & EQUIPMENT
Plant | ID | Hrs | Vehicles | ID | QTY | Site Facilities | ID | Qty
IT Loader | LD011 | 4 | Hilux | DLV90 | 1 | Office 40ft | 9255540 | 1
Wacker Neuson DPU | DPC15 |  | Hilux | 1DLV04 | 1 | Sea Container 20ft | 951200 | 1
Watercart | A119 | 8 |  |  |  | Site Sentry Tower | NA | 2
8T Excavator | AMG 014 |  |  |  |  | Skip Bin | NA | 1
Mini Tipper | SLS04 | 6 |  |  |  | Hydrocarbon Bund | NA | 1
Skid Steer | SLS03 | 2 |  |  |  | Temp Fence | NA | 1
1t Excavator | SLS02
1t Excavator | DEX30 | 2
8T Excavator (Wheeled) | BCC12 | 4
14t Excavator with GPS | EX197 | SD
Roller | R538
0 | Repairs Required |  | NA
0 | Scheduled Service |  | NA
0 | Repairs Required but Operable |  | NA
Total Plant and Equipment Hours:
DELAYS-OPPORTUNITY
Further issues identified with limestone blockwork / kerbing interface as limestone wall depth and finished level trip hazard protection is not compatible with block height nominated in documentation. Survey data collected for potentially problematic paving areas on foreshore/museum intersection and forest street to advise if additional adjustments required. Issues around Watercorp Connection-Connection Date now 29/11/25 impacts to Kerbing, Paving and Concrete works, Watercorp have advised that bacteria testing and another pressure test is required Watercorp Works Request Issued
HSEQ MESSAGES
TCD - Monthly Safety Focus: | Cyclones & Wet Weather
TCD - Daily Safety Focus: | Hydration & Cool zones
Hazards Reported: | Nil
Incident Free Days | 10
Other Notes | NA
INCIDENTS & REPORTS
| QTY | Comments
INCIDENT | 0 | NA
IR | 0 | NA
NCR | 0 | NA
COMMUNICATIONS
TGS MB1119-05 Scheme D implemented
PRODUCTION (CONSTRUCTION STATUS & PROGRESS)
Paving continues along North East
Ongoing Flushing of Waterline in Laneway
Ongoing Prep for planting in Garden Beds on Saturday
Ponding Repairs Undertaken
Photos