## 05
Supervisor Shift Report
Project Name: |  | Batavia Coast Stage 2 | Date: | 2025-11-04
Project Location: |  | Geraldton | Day: | Wednesday
Project No: |  | 1816 | Supervisor | Ultan Toner
Weather Conditions |  | Temp (C): 9-25 | Rain | 0mm | Wind | 10-25 km/h
LABOUR
| Hours | Machine | Start SMU | End SMU | Machine Hrs | Location | Activity | Material | Comments
Direct
MCGAHON,Aideen | 12 | Mini Tipper SLS04 | 998 | 1005.8 |  | Batavia Coast | Load/Haul |  | Load/haul of material from chambers intsection
TONER,Ultan | 12 | Volvo 6T Wheeled Excavator |  |  |  | Batavia Coast | General |  | Boxing out for paving at chambers insection completed
SKINNER,Jamie | 12 | N/A |  |  |  | Batavia Coast | General |  | Excavation for footings for furniture/screeding for paving at chambers
IKHY | 12 | Hitachi ZX180 LD011 | 1022.7 | 1027.7 |  | Batavia Coast | General |  | Worked on building back up 300mm protection around planter boxes
Indirect
Skyline Services
MCAULIFFE,Daniel |  | 1 t Excavator SLS02 |  |  |  | Batavia Coast | General |  | Root deflector installation & excavation for tree root bowls Dewatering
AMG Civil
Griffiths,Ashley |  | N/A |  |  |  | Batavia Coast | Services |  | Cont'd works on trenching on laneway for power for lightpoles
Griffiths,Jackai |  | N/A |  |  |  | Batavia Coast | Services |  | Cont'd works on trenching on laneway for power for lightpoles
Boyle Civil
Henelly,DJ | 12 |  |  |  |  | Batavia Coast | Labouring |  | Working with Ikhy on the planters/re works due to rain
McConnell,Adam | 12 |  |  |  |  | Batavia Coast | Labouring |  | Chambers intersection screeding
Midwest Kerbing
DALY,Troy |  | N/A |  |  |  | Batavia Coast | Concrete/Kerbing
Labourer |  | N/A |  |  |  | Batavia Coast | Concrete/Kerbing
Labourer |  | N/A |  |  |  | Batavia Coast | Concrete/Kerbing
Thinkwater
Warren | [5 empty] | Batavia Coast | Retik
Labourer | [5 empty] | Batavia Coast | Retik
ACP HardStand
Angelo (Contracts Manager) |  | N/A |  |  |  | Batavia Coast | Paving Install |  | Back on site 7th november
JJ | 10 | N/A |  |  |  | Batavia Coast | Paving Install |  | Continue paving install at forest end and moving north
Labourer | 10 | [7 empty] | Continue paving install at forest end and moving north
Kester | 10 | N/A |  |  |  | Batavia Coast | Paving Install |  | Continue paving install at forest end and moving north
HTD Survey
MOSLEY,Josh | [5 empty] | Batavia Coast | Survey |  | Not on site due to inclement weather
TCD Utes/Vechicles
DLV90 Toyota Hilux
DLV04 Toyota Hilux
PLANT NOT IN USE
Machine | Used | Comments
Wacker Neuson DPU DPC15
EX197 14T Sumitomo
Pozi Track 1SLS03
Ped Roller R538
Watercart WC1119
DEX30 1.8T Komatsu
PLANNED WORKS - UPCOMING DAY
Contd paving installation ACP working north from forest
Complete screeding for ACP chambers intersection paving install
Vac out for furniture footings
Works on mortar/patching washouts on planter beds
Dewatering from overnight rain
RISKS - DELAYS - OPPORTUNITY
4hours rain on site/2hours spent on dewatering to prevent further damage
HSEQ
Take Controls
Hazard Cards
Welfare Checks
Water (kL) | 15
Fuel (Total Litres)
INCIDENTS & REPORTS
NIL
COMMUNICATIONS
Glenn (Porters) on site and went through questions and quieries we had all are now in a email from Amit & Dan
Daily Work Extension
1x load of road base delivered to site
ACP HardStand had 1x load of sand delivered (semi load)
Temp fencing adjacent to sump installed
Daily Work Photos