## 21
Supervisor Shift Report
Project Name: |  | Batavia Coast Stage 2 | Date: | 2025-10-21
Project Location: |  | Geraldton | Day: | Tuesday
Project No: |  | 1816 | Supervisor | Ultan Toner
Weather Conditions |  | Temp (C): 9-25 | Rain | 0mm | Wind | 10-25 km/h
LABOUR
| Hours | Machine | Start SMU | End SMU | Machine Hrs | Location | Activity | Material | Comments
Direct
MCGAHON,Aideen |  | Watercart WC1119 |  |  | 0 | Batavia Coast | Conditioning
MCGAHON,Aideen |  | Mini Tipper SLS04 |  |  | 0 | Batavia Coast | Load & Haul
IKHY |  | 1 t Excavator SLS03 |  |  | 0 | Batavia Coast
IKHY |  | Hitachi ZX180 LD011 |  |  | 0 | Batavia Coast
TONER,Ultan |  | Volvo Wheeled 6T |  |  | 0 | Batavia Coast | Storm Lids
SKINNER,Jamie
Indirect
Skyline Services
MCAULIFFE,Daniel |  | 1 t Excavator SLS03 |  |  | 0 | Batavia Coast
AMG Civil
Griffiths,Ashley |  | N/A |  |  |  | Batavia Coast | Services |  | Pit and lid installation
Griffiths,Jackai |  | N/A |  |  | 0 | Batavia Coast | Services |  | Pit and lid installation
Boyle Civil
KEADY,Brendan |  | 14t Excavator EX197 |  |  | 0 | Batavia Coast | Final Trim
McConnel,Adam |  |  |  |  | 0 | Batavia Coast | Labourer
AMG Civil
Griffiths,Ashley |  | N/A |  |  |  | Batavia Coast | Services
Griffiths,Jackai |  | N/A |  |  | 0 | Batavia Coast | Services
HTD Survey
MOSLEY,Josh |  | N/A |  |  | 0 | Batavia Coast | Survey
Cat West
TCD Utes/Vechicles
DLV90 Toyota Hilux
DLV04 Toyota Hilux |  |  |  |  | 0
PLANT NOT IN USE
Machine | Used | Comments
Wacker Neuson DPU DPC15
PLANNED WORKS - UPCOMING DAY
Troy daly onsite (midwest kerbing with intention to start works tomorrow on kerbing)
Cat west on site continue paving works
Dan & Aideen Start work boxing out at bayley/side of country builders
Superstruct back on site to pour ramps and start works on disabled bay ramp (Frank and bobcat on site also to start verge works for pavers)
Brendan & Adam continue verge trimming @ chambers
RISKS - DELAYS - OPPORTUNITY
Nil
HSEQ
Take Controls
Hazard Cards
Welfare Checks
Water (kL) | 15
Fuel (Total Litres)
INCIDENTS & REPORTS
Nil
COMMUNICATIONS
UT & JS sent whatsapp of paving in the evening as its uneven when the shadows are seen
Agreed with superstuct
Daily Work Extension
Cat west completed from C-link ramp to chambers intersection & cont'd through to monument with car park spaces
AMG cont'd work on NBN pits and lids
Works cont'd on excations for midwest kerbing @ chambers and the intersection
Trimmig @ verge contd chambers
Superstruct complete forming of forest end ramps
Daily Work Photos