## 11
Supervisor Shift Report
Project Name: |  | Batavia Coast Stage 2 | Date: | 2025-10-06
Project Location: |  | Geraldton | Day: | Monday
Project No: |  | 1816 | Supervisor | Ultan Toner
Weather Conditions |  | Temp (C): 9-25 | Rain | 0mm | Wind | 10-25 km/h
LABOUR
| Hours | Machine | Start SMU | End SMU | Machine Hrs | Location | Activity | Material | Comments
Direct
MCGAHON,Aideen |  | Watercart WC1119 | 21492 | 21519 | 27 | Batavia Coast | Conditioning |  | Working with vac truck/concreters/dust suppression
MCGAHON,Aideen |  | Mini Tipper SLS04 | 829.9 | 834 | 4.1 | Batavia Coast | Load & Haul |  | load and haul of road base/ hand work while brendan trenching for kerbing/Steel plate x3 exposing
IKHY |  | 1 t Excavator SLS03 | 914 | 921 | 7 | Batavia Coast
HANLY,Thomas |  | Hitachi ZX180 LD011 | 637 | 642 | 5 | Batavia Coast
TONER,Ultan |  | Volvo Wheeled 6T | 1667 | 1670.8 | 3.8 | Batavia Coast | Storm Lids
SKINNER,Jamie
Indirect
Skyline Services
MCAULIFFE,Daniel |  | N/A |  |  | 0 | Batavia Coast | Pit Lid Install |  | Worked on exposing 3x steel plates for lid installation
AMG Civil
Goodwin,Noah |  | N/A |  |  |  | Batavia Coast | Services |  | Testing of water mains Passed by both Glenn (Porters) & Steve (Watercorp)
Griffiths,Jackai |  | N/A |  |  | 0 | Batavia Coast | Services |  | Testing of water mains
Boyle Civil
KEADY,Brendan |  | 1 t Excavator SLS03 | 631 | 637 | 6 | Batavia Coast | Trenching |  | Start trenching for kerbing x1, Expsosing steel plates for lid installation @ bayley
KEADY,Brendan |  | Hitachi ZX180 LD011 | 913.5 | 914 | 0.5
Midwest Kerbing
[6 empty] | Batavia Coast | Concrete/Kerbing
[6 empty] | Batavia Coast | Concrete/Kerbing
[6 empty] | Batavia Coast | Concrete/Kerbing
AMG Civil
Griffiths,Ashley |  | N/A |  |  |  | Batavia Coast | Services |  | Testing of water mains Passed by both Glenn (Porters) & Steve (Watercorp)
Griffiths,Jackai |  | N/A |  |  | 0 | Batavia Coast | Services |  | Testing of water mains
Gavin | [5 empty] | Batavia Coast
HTD Survey
MOSLEY,Josh |  | N/A |  |  | 0 | Batavia Coast | Survey |  | Heights given @ bayley for the setting of stormwater lids
TCD Utes/Vechicles
DLV90 Toyota Hilux
DLV04 Toyota Hilux |  |  |  |  | 0
PLANT NOT IN USE
Machine | Used | Comments
Wacker Neuson DPU DPC15
5t Excavator A118
14t Excavator EX197
Smooth Drum Roller RR 03 |  | Cleaned inside for offhire
Multi Roller 256 |  | Cleaned inside for offhire
PLANNED WORKS - UPCOMING DAY
Back fill trench in 300mm lifts along chambers to the intersection
Start works on re-installation of 25mm laterals along chambers
Install gas tape along side laterals and send to Chris herring as proof
General tidy around site for next weeks works
Removal of any material from boxing out for wombat ramps
All perimeter fencing checked before COB
RISKS - DELAYS - OPPORTUNITY
Nil
HSEQ
Take Controls
Hazard Cards
Welfare Checks
Water (kL) | 30
Fuel (Total Litres)
INCIDENTS & REPORTS
Nil
COMMUNICATIONS
New Rev. of kerbing drawing issued
New Rev. of signage drawing issued @ Dan Griffiths ordered extra signs 1x month lead time
Troy Midwest kerbing on site to go through works/ Agreed on site that he would have 2x installers on site 06/10 and troy himself will be on site 13/10 (TCD to complete trenching as agreed on site) | [8 empty] | Now changhed to the 07/10
Daily Work Extension
Formwork of wombat ramps at chambers/monument intersection completed including concrete
Vac truck works completed
Atco back on site to witness test holding for 24hrs completed and passed
Excavation works contd on trenching for midwest kerbing (TCD to complete this to keep in line with program) x1 completed
Start off hire SD Roller,Multi Roller,5T Excavator cleaing etc
Paul vermeer on site to raise water corp lid and review 3x lids have been raised ready to be checked monday by HDT 1 lid outstanding
Daily Work Photos