## 22
Supervisor Shift Report
Project Name: |  | Batavia Coast Stage 2 | Date: | 2025-09-22
Project Location: |  | Geraldton | Day:
Project No: |  | 1816 | Supervisor | Ultan Toner
Weather Conditions |  | Temp (C): 17-27 | Rain | 0mm | Wind | 27-45 km/h
LABOUR
| Hours | Machine | Start SMU | End SMU | Machine Hrs | Location | Activity | Material | Loads | Comments
Direct
MCGAHON,Aideen | 12 | Watercart WC1119 | 21114 | 21170 | [5 empty] | Ground Prep from Lot 109 to Bayley
MCGAHON,Aideen |  | Smooth Drum Roller RR 03 | 2839 | 2848 | [5 empty] | Ground Prep from Lot 109 to Bayley
MCGAHON,Aideen |  | Multi Roller 256 | 1637 | 1637.8 | [5 empty] | Rolling post spray sealing
HANLY,Tom | 12 | 1 t Excavator SLS03 | [7 empty] | Excavation for limestone blocks
ASHMATULLAYEV,Ikhiyar | 12 | Mini Tipper SLS05 | 15785 | 15947 | [5 empty] | Excavation for limestone blocks
HANLY,Tom |  | Hitachi ZX180 | [7 empty] | General duties
Indirect
Skyline Services | [9 empty] | Ground Prep from Lot 109 to Bayley
McAULIFFE, Daniel | 10 | Grader SLS01 | [7 empty] | Ground Prep from Lot 109
McAULIFFE, Daniel |  | Positrak SSL SSL08 | 1861 | 1866.6
Moordit
Mullin,Conall | 12 | 14t Excavator EX197 | 1399 | 1406 | [5 empty] | Boxing out for paving along Lot 100 and start works on sump final trimming
Geraldton Natural L-Stone
Wyatt,Graham | 1
Mobing to site
Catwest
Aiden | 1 | [8 empty] | Completed C-link spray sealAll inductions done from previous
Samuek | 1 | [8 empty] | Completed C-link spray sealAll inductions done from previous
Nick | 1 | [8 empty] | Completed C-link spray sealAll inductions done from previous
PLANT NOT IN USE
Machine | Used | Comments
Wacker Neuson DPU DPC15
8T Excavator AMG 014
5t Excavator A118
6 Wheel Tipper T091
PLANNED WORKS - UPCOMING DAY
Testing @ bayley
Limestone block install continued
Trenching continued for limestone blocks
Conplant roller serviced
Prep for HSE audit
RISKS - DELAYS - OPPORTUNITY
HSEQ
Take Controls
Hazard Cards
Welfare Checks
Water (kL)
Fuel (Total Litres)
INCIDENTS & REPORTS
Nil
COMMUNICATIONS
Cheryl Thompson on site to continue works for upcoming audit.
Daily Work Extension
Cement stabe completed of HV @ bayley street
Import 5x loads of top soil material for planting bedding
Daily Work Photos

## 23
Supervisor Shift Report
Project Name: |  | Batavia Coast Stage 2 | Date: | 2025-09-23
Project Location: |  | Geraldton | Day:
Project No: |  | 1816 | Supervisor | Ultan Toner
Weather Conditions |  | Temp (C): 18-34 | Rain | 0mm | Wind | 15-25 km/h
LABOUR
| Hours | Machine | Start SMU | End SMU | Machine Hrs | Location | Activity | Material | Loads | Comments
Direct
MCGAHON,Aideen
HANLY,Tom
ASHMATULLAYEV,Ikhiyar
Indirect
HTD
Mosely,Josh
Skyline Services
McAULIFFE, Daniel
O'BRIEN, Jamie
Moordit
Mullin,Conall
Geraldton Natural L-Stone
Wyatt,Graham
PLANT NOT IN USE
Machine | Used | Comments
Komatsu WA320 FWL18
Wacker Neuson DPU DPC15
Watercart WC04
8T Excavator AMG 014
Mini Tipper SLS05
1 t Excavator SLS03
14t Excavator EX197
5t Excavator A118
Smooth Drum Roller RR 03
Multi Roller 256
Positrak SSL SSL08
6 Wheel Tipper T091
Grader SLS01
PLANNED WORKS - UPCOMING DAY
RISKS - DELAYS - OPPORTUNITY
HSEQ
Take Controls
Hazard Cards
Welfare Checks
Water (kL)
Fuel (Total Litres)
INCIDENTS & REPORTS
Nil
COMMUNICATIONS
Daily Work Extension
Daily Work Photos

## 24
Supervisor Shift Report
Project Name: |  | Batavia Coast Stage 2 | Date: | 2025-09-24
Project Location: |  | Geraldton | Day:
Project No: |  | 1816 | Supervisor | Ultan Toner
Weather Conditions |  | Temp (C): 18-34 | Rain | 0mm | Wind | 15-25 km/h
LABOUR
| Hours | Machine | Start SMU | End SMU | Machine Hrs | Location | Activity | Material | Loads | Comments
Direct
MCGAHON,Aideen | 12 | Watercart WC04 | [7 empty] | Ground Prep from Lot 109
MCGAHON,Aideen |  | Smooth Drum Roller RR 03
HANLY,Tom | 12 | 1 t Excavator SLS03
ASHMATULLAYEV,Ikhiyar | 12 | Mini Tipper SLS05
HANLY,Tom |  | Hitachi ZX180
Indirect
HTD
Mosely,Josh | [9 empty] | Survey support
Skyline Services | [9 empty] | Ground Prep from Lot 109 to Bayley
McAULIFFE, Daniel | 10 | Grader SLS01 | [7 empty] | Ground Prep from Lot 109
McAULIFFE, Daniel |  | Positrak SSL SSL08
Moordit
Mullin,Conall | 12 | 14t Excavator EX197
Geraldton Natural L-Stone
Wyatt,Graham | 1 | [8 empty] | Mobing to site
PLANT NOT IN USE
Machine | Used | Comments
Wacker Neuson DPU DPC15
8T Excavator AMG 014
5t Excavator A118
Multi Roller 256
6 Wheel Tipper T091
PLANNED WORKS - UPCOMING DAY
RISKS - DELAYS - OPPORTUNITY
HSEQ
Take Controls
Hazard Cards
Welfare Checks
Water (kL)
Fuel (Total Litres)
INCIDENTS & REPORTS
Nil
COMMUNICATIONS
Daily Work Extension
Daily Work Photos

## 25
Supervisor Shift Report
Project Name: |  | Batavia Coast Stage 2 | Date: | 2025-09-25
Project Location: |  | Geraldton | Day:
Project No: |  | 1816 | Supervisor | Ultan Toner
Weather Conditions |  | Temp (C): 18-34 | Rain | 0mm | Wind | 15-25 km/h
LABOUR
| Hours | Machine | Start SMU | End SMU | Machine Hrs | Location | Activity | Material | Loads | Comments
Direct
MCGAHON,Aideen
HANLY,Tom
ASHMATULLAYEV,Ikhiyar
Indirect
HTD
Mosely,Josh
Skyline Services
McAULIFFE, Daniel
O'BRIEN, Jamie
Moordit
Mullin,Conall
Geraldton Natural L-Stone
Wyatt,Graham
PLANT NOT IN USE
Machine | Used | Comments
Komatsu WA320 FWL18
Wacker Neuson DPU DPC15
Watercart WC04
8T Excavator AMG 014
Mini Tipper SLS05
1 t Excavator SLS03
14t Excavator EX197
5t Excavator A118
Smooth Drum Roller RR 03
Multi Roller 256
Positrak SSL SSL08
6 Wheel Tipper T091
Grader SLS01
PLANNED WORKS - UPCOMING DAY
RISKS - DELAYS - OPPORTUNITY
HSEQ
Take Controls
Hazard Cards
Welfare Checks
Water (kL)
Fuel (Total Litres)
INCIDENTS & REPORTS
Nil
COMMUNICATIONS
Daily Work Extension
Daily Work Photos

## 26
Supervisor Shift Report
Project Name: |  | Batavia Coast Stage 2 | Date: | 2025-09-26
Project Location: |  | Geraldton | Day: | Friday
Project No: |  | 1816 | Supervisor | Ultan Toner
Weather Conditions |  | Temp (C): 18-34 | Rain | 0mm | Wind | 15-25 km/h
LABOUR
| Hours | Machine | Start SMU | End SMU | Machine Hrs | Location | Activity | Material | Loads | Comments
Direct
MCGAHON,Aideen | 11 | Watercart WC1119 |  |  | 0 | Batavia Coast |  |  |  | Conditioning material @ Bayley sub base
MCGAHON,Aideen |  | Smooth Drum Roller RR 03 |  |  | 0 | Batavia Coast |  |  |  | Compaction @ Bayley pre proof roll
HANLY,Tom | 11 | 5t Excavator A118 |  |  | 0 | Batavia Coast |  |  |  | Exposing retik on chambers and removal, Start trench for water mains and gas mains
HANLY,Tom |  | Mini Tipper SLS05 |  |  | 0 | Batavia Coast |  |  |  | Removal of excavated material from chambers trench
ASHMATULLAYEV,Ikhiyar | 11 | 1 t Excavator SLS03 |  |  | 0 | Batavia Coast |  |  |  | Clearing around permenant fencing adjacent to train station
Indirect
Skyline Services
McAULIFFE, Daniel | 10 | Hitachi ZX180 |  |  | 0 | Batavia Coast |  |  |  | General duties/pushing up base course
Moordit
Mullin,Conall | 11 | n/a |  |  | 0 |  |  |  |  | Spotter for 5T excavator on chambers
Geraldton Natural L-Stone
Joy Delmalata | 10 | [8 empty] | Limestone block installation
Sean Delmalata | 10 | [8 empty] | Limestone block installation
FAAIL NHITC | 10 | [8 empty] | Limestone block installation
Blacktop Testing
| 1 | [8 empty] | MMD testing completed on sub base prepped surface
PLANT NOT IN USE
Machine | Used | Comments
Wacker Neuson DPU DPC15
8T Excavator AMG 014
5t Excavator A118
Multi Roller 256
6 Wheel Tipper T091 |  | Off Hired-Paper work/Photos emailed
1 t Excavator SLS03
Grader SLS01
Positrak SSL SSL08
PLANNED WORKS - UPCOMING DAY
Works for next week
Continue final lift of base courses
Concreters on site Tuesday 30th
Vac truck on site Tuesday 30th
Rubber duck delivered to site Tuesday 30th
AMG civil on site Tuesday 30th
RISKS - DELAYS - OPPORTUNITY
Nil
HSEQ
Take Controls
Hazard Cards
Welfare Checks
Water (kL)
Fuel (Total Litres)
INCIDENTS & REPORTS
Nil
COMMUNICATIONS
New Rev. of kerbing drawing issued
Daily Work Extension
Import of sub base material continued until 4.55pm
Testing completed @ bayley including proof rolling
Daily Work Photos

## 30
Supervisor Shift Report
Project Name: |  | Batavia Coast Stage 2 | Date: | 2025-09-30
Project Location: |  | Geraldton | Day: | Tuesday
Project No: |  | 1816 | Supervisor | Ultan Toner
Weather Conditions |  | Temp (C): 15-28 | Rain | 0mm | Wind | 10-30 km/h
LABOUR
| Hours | Machine | Start SMU | End SMU | Machine Hrs | Location | Activity | Material | Comments
Direct
MCGAHON,Aideen | 11 | Watercart WC1119 | 21319 | 21352 |  | Batavia Coast | Conditioning | Road Base | Conditioning material @ Bayley sub base
MCGAHON,Aideen |  | Smooth Drum Roller RR 03 | 2865 | 2871 |  | Batavia Coast | Compaction | Road Base | Compaction @ Bayley pre proof roll
TONER,Ultan |  | Hitachi ZX180 LD011 | 1634 | 1637.8
Indirect
Skyline Services
McAULIFFE, Daniel | 10.5 | Cat 140m Grader SLS01 | 15820 | 15828 |  | Batavia Coast | Grading |  | General duties/pushing up base course
McAULIFFE, Daniel |  | Positrak SSL SSL08 |  |  |  | Batavia Coast |  |  | Excavate sump for vac truck to tip off waste on Lots
AMG Civil
Griffiths,Ashley | 10 | 8T Excavator AMG 014 |  |  |  | Batavia Coast |  |  | Evcavating trench for water and gas @ chambers
Griffiths,Jackai | 10 | N/A |  |  |  | Batavia Coast |  |  | Water pipework installation from foreshore up chambers 75% complete
Boyle Civil
KEADY,Brendan | 11 | 14t Excavator EX197 | 1434 | 1440 |  | Batavia Coast | Final Trim |  | Trimming batters on train station car park end
Super Struct | [8 empty] | Start works from forrest end forming wombat ramps/bike ramps/pram ramps/earthworks completed
FERSTAT,Blair | 10 | N/A |  |  |  | Batavia Coast |  |  | Start works from forrest end forming wombat ramps/bike ramps/pram ramps
PHILLINS,Terry | 10 | N/A |  |  |  | Batavia Coast |  |  | Start works from forrest end forming wombat ramps/bike ramps/pram ramps
BADAT,Mitch | 10 | N/A |  |  |  | Batavia Coast
HTD Survey
WATROS,Wayne |  | N/A | [6 empty] | Survey setout of extra wombat crossing on monument and checking issues on site
iVac | [5 empty] | Batavia Coast |  |  | Indtucions completed & Vac work started at Chambers/monument intersection
KELLY,Aidan |  | N/A |  |  |  | Batavia Coast |  |  | Indtucions completed & Vac work started at Chambers/monument intersection
NEWELL,Mah |  | N/A
Geraldton Natural L-Stone | [5 empty] | Batavia Coast
DELMALATA,Delmalata | 10 | N/A |  |  |  | Batavia Coast |  |  | Limestone block installation
DELMALATA,Sean | 10 | N/A |  |  |  | Batavia Coast |  |  | Limestone block installation
BANIAGE,HUMBLE | 10 | N/A | [6 empty] | Limestone block installation
TCD Utes/Vechicles
DLV90 Toyota Hilux |  |  | 130473 | 130508
DLV04 Toyota Hilux
PLANT NOT IN USE
Machine | Used | Comments
Wacker Neuson DPU DPC15
5t Excavator A118
Mini Tipper SLS05
1 t Excavator SLS03
Multi Roller 256
R538 Small Roller S/D
1 t Excavator SLS03
PLANNED WORKS - UPCOMING DAY
Concrete pour 6.30am @ laydown ramp
Contd vac at area for AMG mains water installation
Vac on foreshore for chris herring gas
Forming of ramps superstruct
RISKS - DELAYS - OPPORTUNITY
Nil
HSEQ
Take Controls
Hazard Cards
Welfare Checks
Water (kL)
Fuel (Total Litres)
INCIDENTS & REPORTS
Nil
COMMUNICATIONS
New Rev. of kerbing drawing issued
Daily Work Extension
Daily Work Photos